## Risk Register New
Risk Number | Risk Detail | Risk Category | Gross Risk Assessment | [5 empty] | Planned Response/Mitigation | Net Risk Assessment | [5 empty] | Risk After Mitigation/Appetite for Risk | Date and Owner
|  |  | Probability |  | Impact |  | Risk Score |  |  | Probability |  | Impact |  | Risk Score
R001 | Policy Appraisal: Poor Quality Lack of consultation | Strategic | 1 | Remote | 3 | Moderate | 3 | Low | Advised by Government of relevant policy changes and Partnership Director and Officers regularly looking out for further policies and responding accordingly. Consultative forums also enable greater visibility and integration of local policies into regional strategy. | 1 | Remote | 2 | Minor | 2 | Low | Low. Partnership staff also continue to monitor their networks for relevant policy discussions. RTS re-write process underway. Tolerate | Nov 2019 June 2020 Partnership Director
R002 | Project Appraisal and Delivery: Incomplete or of poor quality Late Delivery | Reputational | 2 | Unlikely | 4 | Major | 8 | Medium | Monthly monitoring and management intervention by the project officer and oversight by the Programmes Manager. | 2 | Unlikely | 3 | Moderate | 6 | Low | Low. Regular monitoring and management/project team meetings provides all across the organisation with a clear view of progress and expenditure against budget. Regular reports presented to P&A Committee and Partnership Board, which have been revivsed to provide focused monitoring template. Tolerate | Nov 2019 June 2020 Programmes Manager
R003 | Digital/IT: Server failure Comms failure: phones Website | System and Technology | 3 | Possible | 4 | Major | 12 | Medium | SEStran has an up-to-date Management Plan for Business Continuity. Wesbite maintained under contract. Both proactively managed by third parties. | 3 | Possible | 2 | Minor | 6 | Low | Low. Contracted IT consultants deliver IT services. Website contract includes security updates. Robust Information Security Policy in place with regular monitoring reports. GDPR compliant and Cyber Essentials Accreditation achieved. Tolerate | Nov 2019 September 2020 Business Manager
R004 | Reputation: Regard by the public and stakeholders. Negative or inaccurate media coverage leading to misrepresentation of SEStran position | Reputational | 3 | Possible | 3 | Moderate | 9 | Medium | Good relationships with media. Quick response to negative or inaccurate coverage. Proactive placement of copy. Agreed broad media positions. Availability of Spokesperson - Senior staff only. No unauthorised media statements. | 3 | Possible | 2 | Minor | 6 | Low | Low. Partnership staff continue to promote and advocate activities via speaking, writing or wider networking Continue to work closely with regional partners Tolerate | Nov 2019 June 2020 Partnership Director
R005 | Statutory Duties: Failure to adhere to duties described in legislation and related documentation | Legal and Regulatory | 1 | Remote | 4 | Major | 4 | Low | Audit approved systems of governance in place. External and internal audits carried out. | 1 | Remote | 2 | Minor | 2 | Low | Low. Regular monitoring and programming of statutory duties is undertaken by the Partnership Director, Senior Partnership Manager and Business Manager. Audited by third parties. Tolerate | June November 2020 Partnership Director
R006 6.0 | Financial: Significant deviation from budgeted spend | Financial | 2 | Unlikely | 3 | Moderate | 6 | Low | The Partnership's Financial Rules do not permit the Partnership’s spending (whether revenue or capital) to exceed its available budget. Budget and spend is monitored on a monthly basis by SEStran officers, using financial information provided by City of Edinburgh Council (CEC) through the Partnership's Financial Services Service Level Agreement with CEC and supported by qualified accounting staff of CEC. Action is taken by Partnership officers to develop alternative savings measures, including options for development of contingency arrangements, if required and subject to approval by the Partnership. The Partnership's Financial Rules require reporting of financial performances to the Partnership Board on a quarterly basis. | 1 | Remote | 2 | Minor | 2 | Low | Low. In October 2017, the Scottish Government commenced consultation to give consideration to RTPs being given powers to of carry forward of expenditure across financial years. Transport (Scotland) Act 2019 Bill currently going through parliament includesd section on RTPs carrying reserves. Tolerate | March November 2020 Partnership Director
6.1 | The approved budget for 2019/20 assumes provision for a pay award of 3%, based on alignment with the Scottish Government’s public sector pay offer. A 1% increase in pay award uplift equates to an increase in cost of approximately £4,911. | Financial | 4 | Probable | 1 | Insignificant | 4 | Low | Alignment with Scottish Local Government pay policy | 4 | Probable | 1 | Insignificant | 4 | Low | Low Tolerate | March November 2020 Partnership Director
6.2 | Staff recharges - EU projects: The proposed budget assumes that £119,000 of staff time can be recharged to five EUProjects - Share-north, Surflogh, Bling, Primaas and Connect. There is a risk this may not be achievable | Financial | 5 | Highly Probable | 3 | Moderate | 15 | High | Any shortfall in employee recharges will be managed through corresponding reductions in Projects Budget expenditure. In 2020/21, EU projects represent 14% of the proposed budget. | 4 | Probable | 2 | Minor | 8 | Medium | Medium: Other funding sources will continue to be pursued. Tolerate | March November 2020 Partnership Director
6.3 | Inflation: There is a risk that the approved budget does not adequately cover price inflation and increasing demand for services. | Financial | 3 | Possible | 4 | Major | 12 | Medium | When setting the revenue budget, allowance made for specific price inflation and budgets adjusted in line with current cost forecasts. | 3 | Possible | 4 | Major | 12 | Medium | Medium Tolerate | March November 2020 Partnership Director
6.4 | Delays in payment of external grants results in additional short-term borrowing costs. | Financial | 3 | Possible | 2 | Minor | 6 | Low | SEStran grant claims for projects are submitted in compliance with grant funding requirements to ensure minimal delay in payment. Ongoing monitoring of cash flow is undertaken to manage exposure to additional short-term borrowing costs. | 3 | Possible | 1 | Insignificant | 3 | Low | Low: Grant submission procedures in place, along with financial planning. Tolerate | March November 2020 Partnership Director
6.5 | Sources of additional income to the Partnership may become constrained in the current economic climate and/or due to changes in operating arrangements. | Financial | 4 | Probable | 3 | Moderate | 12 | Medium | Active Travel funding a high priority for Government with funds consistently available to bid for. Revenue budget for 2020/21 developed to take account of most likely level of external income in 2020/21. | 4 | Probable | 3 | Moderate | 12 | Medium | Medium Tolerate: Adapt expenditure accordingly | March November 2020 Partnership Director
6.6 | Funding reductions: Future reductions in core funding from Scottish Government and/or council requisitions. This could result in difficulty in delivering statutory obligations/duties. | Financial | 3 | Possible | 4 | Major | 12 | Medium | The Partnership will continue to source and develop external funding. Working with the Scottish Government on a regional response to the pandemic should increase likelihood of funding remaining constant if not increasing. | 3 | Possible | 4 | Major | 12 | Medium | Medium Tolerate: Manage organisation in accordance with available funding but ability of organisation to deliver RTS objectives will inevitably be dictated by available funding. Scottish Government now promoting 3 year budget process, providing more certaintity for future planning. | March November 2020 Partnership Director
6.7 | The deficit on the staff pension fund could lead to increases in the employers pension contribution | Financial | 4 | Probable | 3 | Moderate | 12 | Medium | Following the Lothian Pension Fund Triennial Acturial Review of 2017, Partnership contribution rates have been advised until 2020/21. The risk is therefore for future years. | 4 | Probable | 3 | Moderate | 12 | Medium | Medium Tolerate | March November 2020 Partnership Director
6.8 | Current staffing levels cannot be maintained due to funding constraints and the Partnership incurs staff release costs | Financial | 3 | Possible | 4 | Major | 12 | Medium | The Partnership continues to seek additional sources of funding for activities aligned to the Partnership's objectives to supplement resources Recruitment control measures in place. Additional resources can be managed through consultancy as required. | 3 | Possible | 4 | Major | 12 | Medium | Medium: Other funding sources will continue to be pursued. Tolerate | March November 2020 Partnership Director
6.9 | Following the outcome of the EU Referendum, the Partnership is unable to access EU funding. | Financial | 5 | Highly Probable | 3 | Moderate | 15 | High | The Partnership continues to seek alternative funding sources to progress knowledge exchange/transfer and to seek to successfully bid for EU projects following the United Kingdom servicing notice under Article 50. | 4 | Probable | 3 | Moderate | 12 | Medium | Medium Tolerate: Adapt expenditure accordingly Currently involved in 6 EU projects, the completion of which are underwritten by the UK Treasury. | March November 2020 Partnership Director
R007 | HR: Pension Liabilities Redundancy Contingency Inappropiate Behaviour Staffing/Incapacity | People | 3 | Possible | 3 | Moderate | 9 | Medium | SLA in place with Falkirk Council to provide specialist HR advice as required and is under regular review. Legal advice is provided, when required, through a framework contract, which is in place until 31 May 2022. | 1 | Remote | 2 | Minor | 2 | Low | Low Tolerate | June Nov 2019 20 Partnership Director
R008 | Corporate: Removal of RTPs as part of the review of the National Transport Strategy. Regional governance review. | Strategic | 4 | Probable | 4 | Major | 16 | High | RTPs jointly lobbying Transport Minister. SEStran is engaged in the NTS2 review, representing all RTPs on the NTS2 Review Board and has sought and received assurances around retention of functions and undertakings transfer from Scottish Ministers. NTS2 Roles and Responsibilities Working Group have made recommendations which are currently being considered by Transport Scotland. Discussions ongoing with Transport Scotland who have indicated they are receptive to enhanced role for RTPs during current phase of lockdown release. Joint RTPs paper submitted to Transport Scotland May 2020. | 4 | Probable | 4 | Major | 16 | High | High: Seek to resolve | Nov 2020 Partnership Director
R009 | EU Exit Other Funding Sources: Impact on learning and funding | Financial | 5 | Highly Probable | 3 | Moderate | 15 | High | The Partnership has sought to engage in as many relevant EU projects and funds as it can whilst UK authorities are allowed to access these funds. This should mitigate the short-term impact of any EU Exit negotiated and implemented. Timescales for effective exit remain unclear The Partnership has a proven track record in securing funding for relevant projects from the UK and other partners. It is anticipated that this will continue. | 5 | Highly Probable | 2 | Minor | 10 | Medium | Medium: The risk remains as there is significant uncertainty around the medium (3-5year) horizon for access to funds. Opportunity for renewed collaborative working with EU following Brexit to be explored. SEStran continuing to be accepted as partners in EU funded projects. EU projects secured for further 3 years. Other funding applications will be made when available. Tolerate | Nov 2020 Partnership Director
R010 | Governance: Succession Planning Business Continuity | People | 3 | Possible | 3 | Moderate | 9 | Medium | Governance Scheme contains adequate provision to deal with senior officer absence. Staff structure and Business Continuity Plan in place. Senior Partnership Manager appointed. | 2 | Unlikely | 2 | Minor | 4 | Low | Low Tolerate | Nov 2020 Partnership Director
R011 | Third party Service Level Agreements: Failure or inadequacy of service | People | 2 | Unlikely | 2 | Minor | 4 | Low | Service Level Agreements in place for Financial Services, HR, Legal and Insurance services. Reviewed annually by senior officers. Subject to independent audit scrutiny. | 2 | Unlikely | 2 | Minor | 4 | Low | Low Tolerate | Nov 2020 Partnership Director
RO12 | Pandemic / Epidemic: Interruption of normal service/inability or difficulty delivering functions/loss of service provided by contractor. Changes to delivery of strategy including RTS, where dependent on new and external context/national or regional policy timescales. Financial impact of crisis on sources of funding. New functions required from RTS can't be met from existing resource. | Strategic | 2 | Unlikely | 5 | Catastrophic | 10 | Medium | Regular contact with officials of both Transport Scotland and consituent councils to map a way forward and align with new timescales and new requirements. Current RTP functions can be delivered by working from home. New functions can be met through consultancy support. Procurement and contracts to safeguard against loss of service and identify options for flexibility of delivery. Utilise Covid-19 Act facilities around procurement. Organisation to maintain a 'flexible and nimble' attitude to supporting service delivery. RTS Project is of a scale to have its own detailed 'RAID' log with Risk Register | 2 | Unlikely | 4 | Major | 8 | Medium | Medium: An ongoing risk (realised in March 2020) remains during the Transport Transition Plan and Phases for recovery. An ongoing risk remains for future spikes of Covid-19 or other outbreaks of similar levels of impact. Tolerate | June 2020 Partnership Director

## Closed Risks
Risk Number | Risk Detail | Risk Category | Gross Risk Assessment | [5 empty] | Planned Response/Mitigation | Net Risk Assessment | [5 empty] | Risk After Mitigation/Appetite for Risk | Date and Owner
|  |  | Probability |  | Impact |  | Risk Score |  |  | Probability |  | Impact |  | Risk Score
R005 5.1 | Restricted ability to undertake RTS re-write: Inadequate senior staff resourcing available due to continued absence of Partnership Director | Strategic | 4 | Probable | 3 | Moderate | 12 | Medium | Resolve absence as soon as possible and appoint external resources as required. | 2 | Unlikely | 2 | Minor | 4 | Low | Partnership Director appointed May 2019. Funds identified for RTS re-write | June 2019 CLOSED
6.9 | Accommodation: Occupancy Agreeement with SG due for renewal February 2019. SG may not renew and alternative premises required at market rates. | Financial | 3 | Possible | 3 | Moderate | 9 | Medium | A notice period of 12 months must be served by each party under the current occupancy agreement. Occupancy Agreement renewed until February 2022. | 3 | Possible | 3 | Moderate | 9 | Medium |  | June 2019 CLOSED
6.1 | ECOMM: Agreement to commit to ECOMM on the basis of being cost neutral. Income depends on number of delegates attending conference. | Financial | 3 | Possible | 3 | Moderate | 9 | Medium | SEStran withdrew offer to host ECOMM due to uncertaintity over Brexit and subsequent impact on attendance at the conference. | 3 | Possible | 2 | Minor | 6 | Low |  | June 2019 CLOSED

## DATA
Likelihood |  | Severity |  | Risk Score |  | At Risk | Impact |  |  |  |  | Impact
1 | Remote | 1 | Insignificant | 1 | Low Risk | System and Technology | Descriptor | Score | Health and Safety Impact | Impact on Service and Reputation | Financial Impact | Catastrophic | 5 | 10 | 15 | 20 | 25
2 | Unlikely | 2 | Minor | 2 |  | Reputational | Insignificant | 1 | No injury or no apparent injury. | No impact on service or reputation. Complaint unlikely, litigation risk remote. | Loss/costs up to £5000. | Major | 4 | 8 | 12 | 16 | 20
3 | Possible | 3 | Moderate | 3 |  | Strategic | Minor | 2 | Minor injury (First Aid on Site) | Slight impact on service and/or reputation. Complaint possible. Litigation possible. | Loss/costs between £5000 and £50,000. | Moderate | 3 | 6 | 9 | 12 | 15
4 | Probable | 4 | Major | 4 |  | Financial | Moderate | 3 | Reportable injury | Some service distruption. Potential for adverse publicity, avoidable with careful handling. Complaint expected. Litigation probable. | Loss/costs between £50,000 and £500,000 | Minor | 2 | 4 | 6 | 8 | 10
5 | Highly Probable | 5 | Catastrophic | 5 |  | Governance | Major | 4 | Major injury (reportable) or permanent incapacity | Service disrupted. Adverse publicity not avoidable (local media). Complaint expected. Litigation expected. | Loss/costs between £500,000 and £5,000,000. | Insignificant | 1 | 2 | 3 | 4 | 5
|  |  |  | 6 |  | Specific Operational | Catastrophic | 5 | Death | Service interrupted for significant time. Adverse publicity not avoidable (national media interest.) Major litigation expected. Resignation of senior management/directors. | Theft/loss over £5,000,000 | Likelihood | Remote | Unlikely | Possible | Probable | Highly Probable
|  |  |  | 8 | Medium Risk | External
|  |  |  | 9 |  | Legal and Regulatory | Likelihood
|  |  |  | 10 |  | People | Descriptor | Score | Example
|  |  |  | 12 |  | Physical | Remote | 1 | May only occur in exeptional circumstances.
|  |  |  | 15 | High Risk |  | Unlikely | 2 | Expected to occur in a few circumstances.
|  |  |  | 16 |  |  | Possible | 3 | Expected to occur in some circumstances.
|  |  |  | 20 |  |  | Probable | 4 | Expected to occur in many circumstances.
|  |  |  | 25 |  |  | Highly Probable | 5 | Expected to occur frequently and in most circumstances.
Maintain existing measures in place.
Review control measures. Even if the risk is low, there may be things that can be done to bring the risk rating down to minimal.
Improve control measures. If the Rating Action Band is greater than 3 or 4 then a review of the exisiting safety/control measures needs to be done, where additional parameters should be put in to bring the risk back to a low or minimal risk. (If it is identified that a hazard which, after applying any applicable control measures, is still rated as a 'medium', then speak to a professional health and safety advisor.)
Improve control measures immediately and consider stopping work activity until risk is reduced.