## Risk Register New
Risk Number | Risk Detail | Risk Category | Gross Risk Assessment | [5 empty] | Planned Response/Mitigation | Net Risk Assessment | [5 empty] | Risk After Mitigation | Date and Owner
|  |  | Probability |  | Impact |  | Risk Score |  |  | Probability |  | Impact |  | Risk Score
R001 | Policy Appraisal: Poor Quality Lack of consultation | Strategic | 1 | Remote | 3 | Moderate | 3 | Low | Advised by Government of relevant policy changes and Partnership Director and Officers regularly looking out for further policies and responding accordingly. Consultative forums also enable greater visibility and integration of local policies into regional strategy. Make full use of online consultancy options. | 1 | Remote | 2 | Minor | 2 | Low | Low. Partnership staff also continue to monitor their networks for relevant policy discussions. Draft RTS approved for statutory consultation. RTS re-write process underway. Tolerate | Ongoing Partnership Director
R002 | Project Appraisal and Delivery: Incomplete or of poor quality Late Delivery | Reputational | 2 | Unlikely | 4 | Major | 8 | Medium | Monthly monitoring and management intervention by the project officer and oversight by the Programmes Manager. Regular monitoring and management/project team meetings provides all across the organisation with a clear view of progress and expenditure against budget. | 2 | Unlikely | 3 | Moderate | 6 | Low | Low. Regular reports presented to P&A Committee and Partnership Board, which have been revivsed to provide focused monitoring template. Tolerate | Ongoing Programmes Manager
R003 | Digital/IT: Server failure Comms failure: phones Website | System and Technology | 3 | Possible | 4 | Major | 12 | Medium | SEStran will reviewed the Management Plan for Business Continuity in August 2021. IT/Wesbite maintained under contract. Both proactively managed by third parties. IT hardware/software/licences upgraded at regular intervals. | 3 | Possible | 2 | Minor | 6 | Low | Low. Contracted IT consultants deliver IT services. Website contract includes security updates. Robust Information Security Policy in place with regular monitoring reports. GDPR compliant and Cyber Essentials Plus Accreditation maintained. Tolerate | Ongoing Business Manager
R004 | Reputation: Regard by the public and stakeholders. Negative or inaccurate media coverage leading to misrepresentation of SEStran position | Reputational | 3 | Possible | 3 | Moderate | 9 | Medium | Good relationships with media. Quick response to negative or inaccurate coverage. Board members regulary updated on SEStran work successes and issues. Proactive placement of copy. Agreed broad media positions. Availability of Spokesperson - Senior staff only. No unauthorised media statements. | 3 | Possible | 2 | Minor | 6 | Low | Low. Partnership staff and Board Members continue to promote and advocate activities via speaking, writing or wider networking Continue to work closely with regional partners Tolerate | Ongoing Partnership Director
R005 | Statutory Duties: Failure to adhere to duties described in legislation and related documentation | Legal and Regulatory | 1 | Remote | 4 | Major | 4 | Low | Board members regulary updated on SEStran work successes and issues. Ongoing monthly liaison with Transport Scotland. Regular liaison with Auditors. | 1 | Remote | 2 | Minor | 2 | Low | Low. Regular monitoring and programming of statutory duties is undertaken by the Partnership Director, Senior Partnership Manager and Business Manager. Audited by third parties. Tolerate | Ongoing Partnership Director
R006 6.0 | Financial: Significant deviation from budgeted spend | Financial | 2 | Unlikely | 3 | Moderate | 6 | Low | The Partnership's Financial Rules do not permit the Partnership’s spending (whether revenue or capital) to exceed its available budget. Budget and spend is monitored on a monthly basis by SEStran officers, using financial information provided by City of Edinburgh Council (CEC) through the Partnership's Financial Services Service Level Agreement with CEC and supported by qualified accounting staff of CEC. Action is taken by Partnership officers to develop alternative savings measures, including options for development of contingency arrangements, if required and subject to approval by the Partnership. The Partnership's Financial Rules require reporting of financial performances to the Partnership Board on a quarterly basis. | 1 | Remote | 2 | Minor | 2 | Low | Low. Transport (Scotland) Act 2019 includes section on RTPs carrying reserves. Tolerate | November 2021 Partnership Director
6.1 | The approved budget for 2021/22 assumes provision for a pay award of 2%, based on alignment with the Scottish Government’s public sector pay offer. A 1% increase in pay award uplift equates to an increase in cost of approximately £5,681. | Financial | 4 | Probable | 1 | Insignificant | 4 | Low | Alignment with Scottish Local Government pay policy. | 4 | Probable | 1 | Insignificant | 4 | Low | Low Tolerate An assessment has been undertaken of the cost of alignment with the current Scottish Local Government pay policy and the proposed pay award remains affordable. | November 2021 Partnership Director
6.2 | Staff recharges - externally funded projects: The approved budget assumes that £119,000 of staff time can be recharged to externally-funded projects. There is a risk this may not be achievable | Financial | 5 | Highly Probable | 3 | Moderate | 15 | High | Any shortfall in employee recharges will be managed through corresponding reductions in Projects Budget expenditure. In 2021/22, externally-funded projects represent 33% of the approved budget. | 4 | Probable | 2 | Minor | 8 | Medium | Medium: Other funding sources will continue to be pursued. Tolerate At 31 October 2021, recharges for 2021/22 are forecast to be greater than the budget target. | November 2021 Partnership Director
6.3 | Inflation: There is a risk that the approved budget does not adequately cover price inflation and increasing demand for services. | Financial | 3 | Possible | 4 | Major | 12 | Medium | When setting the revenue budget, allowance made for specific price inflation and budgets adjusted in line with current cost forecasts. | 3 | Possible | 4 | Major | 12 | Medium | Medium Tolerate | November 2021 Partnership Director
6.4 | Delays in payment of external grants results in additional short-term borrowing costs. | Financial | 3 | Possible | 2 | Minor | 6 | Low | SEStran grant claims for projects are submitted in compliance with grant funding requirements to ensure minimal delay in payment. Ongoing monitoring of cash flow is undertaken to manage exposure to additional short-term borrowing costs. | 3 | Possible | 1 | Insignificant | 3 | Low | Low: Grant submission procedures in place, along with financial planning. Tolerate | November 2021 Partnership Director
6.5 | Sources of additional income to the Partnership may become constrained in the current economic climate and/or due to changes in operating arrangements. | Financial | 4 | Probable | 3 | Moderate | 12 | Medium | Active Travel funding a high priority for Government with funds consistently available to bid for. Revenue budget for 2021/22 developed to take account of most likely level of external income in 2021/22. | 4 | Probable | 3 | Moderate | 12 | Medium | Medium Tolerate: Adapt expenditure accordingly. 2021/22 income recoveries are forecast to be in line with the 2021/22 budget target. | November 2021 Partnership Director
6.6 | Funding reductions: Future reductions in core funding from Scottish Government and/or council requisitions. This could result in difficulty in delivering statutory obligations/duties. | Financial | 3 | Possible | 4 | Major | 12 | Medium | The Partnership will continue to source and develop external funding. Working with the Scottish Government on a regional response to the pandemic should increase likelihood of funding remaining constant if not increasing. | 3 | Possible | 4 | Major | 12 | Medium | Medium Tolerate: Manage organisation in accordance with available funding but ability of organisation to deliver RTS objectives will inevitably be dictated by available funding. Scottish Government now promoting 3 year budget process, providing more certaintity for future planning. | November 2021 Partnership Director
6.7 | The deficit on the staff pension fund could lead to increases in the employers pension contribution | Financial | 4 | Probable | 3 | Moderate | 12 | Medium | Following the Lothian Pension Fund Triennial Acturial Review of 2020, Partnership contribution rates have been advised until 2023/24. Planning assumptions have been updated and included in the indicative revenue budget 2022/23 to 2023/24 reported to the Partnership Board on 19th March 2021. | 4 | Probable | 3 | Moderate | 12 | Medium | Medium Tolerate | November 2021 Partnership Director
6.8 | Current staffing levels cannot be maintained due to funding constraints and the Partnership incurs staff release costs | Financial | 3 | Possible | 4 | Major | 12 | Medium | The Partnership continues to seek additional sources of funding for activities aligned to the Partnership's objectives to supplement resources Recruitment control measures in place. Additional resources can be managed through consultancy as required. | 3 | Possible | 4 | Major | 12 | Medium | Medium: Other funding sources will continue to be pursued. Tolerate | Ongoing Partnership Director
R007 | HR: Pension Liabilities Redundancy Contingency Inappropiate Behaviour Staffing/Incapacity | People | 3 | Possible | 3 | Moderate | 9 | Medium | SLA in place until May 2022 with Falkirk Council to provide specialist HR advice as required and is under regular review. Legal advice is provided, when required, through a framework contract, which is in place until August 2023 | 1 | Remote | 2 | Minor | 2 | Low | Low Tolerate | May 2022 Partnership Director
R008 | Corporate: Regional Governance Review. | Strategic | 4 | Probable | 4 | Major | 16 | High | NTS2 Roles and Responsibilities Working Group have made recommendations which are currently being considered by Transport Scotland. Discussions ongoing with Transport Scotland who have indicated they are receptive to enhanced role for RTPs during current phase of lockdown release. NTS2 Roles and Responsibilities WG resumed meetings in September 2020 to consider regional governance arrangements but has been delayed by TS. Monthly meetings between TS and RTPs established May 2020 | 4 | Probable | 4 | Major | 16 | High | High: Seek to resolve | Ongoing Partnership Director
R009 | Other Funding Sources: Impact on learning and funding | Financial | 5 | Highly Probable | 3 | Moderate | 15 | High | The Partnership has sought to engage in as many relevant EU projects and funds as it can whilst UK authorities are allowed to access these funds. This should mitigate the short-term impact of any EU Exit negotiated and implemented. The Partnership has a proven track record in securing funding for relevant projects from the UK and other partners. It is anticipated that this will continue. | 5 | Highly Probable | 2 | Minor | 10 | Medium | Medium: The risk remains as there is significant uncertainty around the medium (3-5year) horizon for access to funds. Opportunity for renewed collaborative working with EU following Brexit to be explored. SEStran continuing to be accepted as partners in EU funded projects. EU projects secured for further 3 years, with possible extension to two projects. Other funding applications will be made when available. Tolerate | Ongoing Partnership Director
R010 10.1 | Governance: Succession Planning Business Continuity | Governance | 3 | Possible | 3 | Moderate | 9 | Medium | Governance Scheme contains adequate provision to deal with senior officer absence. Staff structure and Business Continuity Plan in place. Senior Partnership Manager appointed. | 2 | Unlikely | 2 | Minor | 4 | Low | Low Tolerate | November 2021 CLOSED Partnership Director
10.2 | Local Government Elections in May 2022 coincides with end of term of NCM's Risk of lack of continuity and loss of expertise. | Governance | 3 | Possible | 3 | Moderate | 9 | Medium | Early a Arrangements for reappointment/recruitment of NCMs are being progressed. A meeting of the Succession Planning Committee is scheduled for Nov 2021. | 2 | Unlikely | 2 | Minor | 4 | Low | Low Tolerate | November 2021 March 2022 Partnership Director
R011 | Third party Service Level Agreements: Failure or inadequacy of service | External | 2 | Unlikely | 2 | Minor | 4 | Low | Service Level Agreements in place for Financial Services, HR, Legal and Insurance services. Reviewed annually by senior officers. Subject to independent audit scrutiny. | 2 | Unlikely | 2 | Minor | 4 | Low | Low Tolerate | November 2021 Partnership Director
RO12 12.0 | Pandemic / Epidemic: Interruption of normal service/inability to deliver functions. Financial impact of crisis on sources of funding. | Strategic | 3 | Possible | 4 | Major | 12 | Medium | Adhere to Government restrictions, rules or guidance. Regular communication with Transport Scotland and consituent councils officials to guide any operational changes. Business Continuity Plan. Maintain current functions that can be delivered within working guidance. | 3 | Possible | 3 | Moderate | 9 | Medium | Medium: An ongoing risk remains for future spikes of Covid-19 or other kinds of disease outbreaks Working from home arrangements now tried and tested and effective. Tolerate | Ongoing Partnership Director
12.1 | Inadequate measures in place to facilitate staff health, safety and well-being during contingency arrangements or future office arrangements. | People | 3 | Possible | 4 | Major | 12 | Medium | Review and update of appropriate policies is underway . Carry out appropriate assessments of office equipment and working arrangements, following landlords guidance in relation to access to the office. Follow mitigating actions identified in the COVID Return to Office Working protocol to protect staff. Further develop Draft Risk Management Framework is being developed for scrutiny by with P&A Committee. Refresh Business Continuity Plan has been reviewed. Liaise with HR Adviser, SG facilities team. New Hybrid Working Policy developed to facilitate Review transition arrangements to normal working arrangements | 3 | Possible | 3 | Moderate | 9 | Medium | Medium An ongoing risk remains for future pandemics and future widespread disease or other outbreaks. Measures will be adjusted in accordance with government advice. Tolerate | September 21 Ongoing Partnership Director (Subject to SG advice)
12.2 | Inadequate measures in place to facilitate staff health, safety and well-being during working from home arrangements. | People | 3 | Possible | 4 | Major | 12 | Medium | Review and update aAppropriate policies are being reviewed and updated . Carry out appropriate rRisk assessments of staff personal home working arrangements have been completed and will be subject to regular review.. Follow mitigating actions identified in the assessment to protect staff. Further develop Risk Management Framework being developed for scrutiny by with P&A Committee. Refresh Business Continuity Plan reviewed and updated Aug 2021. Liaise with HR Adviser. Review transition arrangements to normal working arrangements at appropriate time. Hybrid Working Policy will facilitate this. | 3 | Possible | 3 | Moderate | 9 | Medium | Medium An ongoing risk remains for future pandemics and future widespread disease or other outbreaks. Measures will be adjusted in accordance with government advice and legislation. Tolerate | September 21 Ongoing Partnership Director (Subject to SG advice)

## Closed Risks
Risk Number | Risk Detail | Risk Category | Gross Risk Assessment | [5 empty] | Planned Response/Mitigation | Net Risk Assessment | [5 empty] | Risk After Mitigation/Appetite for Risk | Date and Owner
|  |  | Probability |  | Impact |  | Risk Score |  |  | Probability |  | Impact |  | Risk Score
R005 5.1 | Restricted ability to undertake RTS re-write: Inadequate senior staff resourcing available due to continued absence of Partnership Director | Strategic | 4 | Probable | 3 | Moderate | 12 | Medium | Resolve absence as soon as possible and appoint external resources as required. | 2 | Unlikely | 2 | Minor | 4 | Low | Partnership Director appointed May 2019. Funds identified for RTS re-write | June 2019 CLOSED
6.9 | Accommodation: Occupancy Agreeement with SG due for renewal February 2019. SG may not renew and alternative premises required at market rates. | Financial | 3 | Possible | 3 | Moderate | 9 | Medium | A notice period of 12 months must be served by each party under the current occupancy agreement. Occupancy Agreement renewed until February 2022. | 3 | Possible | 3 | Moderate | 9 | Medium |  | June 2019 CLOSED
6.1 | ECOMM: Agreement to commit to ECOMM on the basis of being cost neutral. Income depends on number of delegates attending conference. | Financial | 3 | Possible | 3 | Moderate | 9 | Medium | SEStran withdrew offer to host ECOMM due to uncertaintity over Brexit and subsequent impact on attendance at the conference. | 3 | Possible | 2 | Minor | 6 | Low |  | June 2019 CLOSED
6.9 | Following the outcome of the EU Referendum, the Partnership is unable to access EU funding. | Financial | 5 | Highly Probable | 3 | Moderate | 15 | High | The Partnership continues to seek alternative funding sources to progress knowledge exchange/transfer. | 4 | Probable | 3 | Moderate | 12 | Medium | Medium Tolerate: Adapt expenditure accordingly Currently involved in 5 EU projects, the completion of which are underwritten by the UK Treasury. | June 2021 CLOSED

## DATA
Likelihood |  | Severity |  | Risk Score |  | At Risk | Impact |  |  |  |  | Impact
1 | Remote | 1 | Insignificant | 1 | Low Risk | System and Technology | Descriptor | Score | Health and Safety Impact | Impact on Service and Reputation | Financial Impact | Catastrophic | 5 | 10 | 15 | 20 | 25
2 | Unlikely | 2 | Minor | 2 |  | Reputational | Insignificant | 1 | No injury or no apparent injury. | No impact on service or reputation. Complaint unlikely, litigation risk remote. | Loss/costs up to £5000. | Major | 4 | 8 | 12 | 16 | 20
3 | Possible | 3 | Moderate | 3 |  | Strategic | Minor | 2 | Minor injury (First Aid on Site) | Slight impact on service and/or reputation. Complaint possible. Litigation possible. | Loss/costs between £5000 and £50,000. | Moderate | 3 | 6 | 9 | 12 | 15
4 | Probable | 4 | Major | 4 |  | Financial | Moderate | 3 | Reportable injury | Some service distruption. Potential for adverse publicity, avoidable with careful handling. Complaint expected. Litigation probable. | Loss/costs between £50,000 and £500,000 | Minor | 2 | 4 | 6 | 8 | 10
5 | Highly Probable | 5 | Catastrophic | 5 |  | Governance | Major | 4 | Major injury (reportable) or permanent incapacity | Service disrupted. Adverse publicity not avoidable (local media). Complaint expected. Litigation expected. | Loss/costs between £500,000 and £5,000,000. | Insignificant | 1 | 2 | 3 | 4 | 5
|  |  |  | 6 |  | Specific Operational | Catastrophic | 5 | Death | Service interrupted for significant time. Adverse publicity not avoidable (national media interest.) Major litigation expected. Resignation of senior management/directors. | Theft/loss over £5,000,000 | Likelihood | Remote | Unlikely | Possible | Probable | Highly Probable
|  |  |  | 8 | Medium Risk | External
|  |  |  | 9 |  | Legal and Regulatory | Likelihood
|  |  |  | 10 |  | People | Descriptor | Score | Example
|  |  |  | 12 |  | Physical | Remote | 1 | May only occur in exeptional circumstances.
|  |  |  | 15 | High Risk |  | Unlikely | 2 | Expected to occur in a few circumstances.
|  |  |  | 16 |  |  | Possible | 3 | Expected to occur in some circumstances.
|  |  |  | 20 |  |  | Probable | 4 | Expected to occur in many circumstances.
|  |  |  | 25 |  |  | Highly Probable | 5 | Expected to occur frequently and in most circumstances.
Maintain existing measures in place.
Review control measures. Even if the risk is low, there may be things that can be done to bring the risk rating down to minimal.
Improve control measures. If the Rating Action Band is greater than 3 or 4 then a review of the exisiting safety/control measures needs to be done, where additional parameters should be put in to bring the risk back to a low or minimal risk. (If it is identified that a hazard which, after applying any applicable control measures, is still rated as a 'medium', then speak to a professional health and safety advisor.)
Improve control measures immediately and consider stopping work activity until risk is reduced.