Final Report

November 2021

East Fife Mobility Hubs Feasibility Study and Business case: St Andrews Mobility Hub

SEStran

Our ref: 24097601

Final Report

November 2021

East Fife Mobility Hubs Feasibility Study and Business case: St Andrews Mobility Hub

| Prepared by: | Prepared for: |
| --- | --- |
| Steer 28-32 Upper Ground London SE1 9PD | SEStran Area 3D (Bridge) Victoria Quay Edinburgh EH6 6QQ |
| +44 20 7910 5000 www.steergroup.com | Our ref: 24097601 |

Contents

1	Introduction	2

Overview	2

Definition of a Mobility Hub	2

Structure of the document	3

2	Mobility Hub assessment	4

Overview	4

Mobility Hub in St Andrews	4

3	Mobility Hubs costs - by option	9

Overview	9

Capital costs	9

Operating costs	11

Managing costs	12

4	Strategic Case – policy rationale and need for intervention	13

Overview	13

Policy review	13

Evidence Base	22

Need for intervention – St Andrews	25

5	Economic Case	29

Overview	29

Scheme costs	29

Scheme demand and benefits	31

Step 1 – base demand for Mobility Hub	32

Step 2a – benefits to existing users	33

Step 2b – forecasting modal shift	34

Step 3a – benefits from modal shift	37

Economic appraisal	38

6	Financial case	41

Overview	41

Scheme investment costs	41

Potential funding options	41

Affordability	44

7	Management case – delivery plan	46

Overview	46

Stage 1 – Planning	46

Stage 2 – Initiation	47

Stage 3 – Implementation	49

Stage 4 – Operations	49

Monitoring and evaluation	51

8	Commercial case – system procurement	55

Overview	55

Procurement	55

9	Conclusion	60

Overview	60

St Andrews Mobility Hub	60

# Introduction

## Overview

Mobility Hubs will be an important tool to support Fife Council as it seeks to meet the aims and objectives outlined in the National Transport Strategy 2 (NTS2), reflected in SEStran’s emerging Regional Transport Strategy (RTS) and in the development of a new Local Transport Strategy (LTS) for Fife. These include reducing inequalities; taking climate action; helping deliver inclusive economic growth; and improving health and wellbeing.

This document presents the technical assessment and business case for a Mobility Hub in St Andrews which could form the basis for a funding submission. This document also examines the costs associated with funding the capital, operating and renewal costs.

It should be noted that shared mobility market is a fast-moving sector, and all assumptions are based on the current data and industry intelligence at the time the report was prepared (October 2021).

## Definition of a Mobility Hub

SEStran defines a Mobility Hub as follows:

“A Mobility Hub is a recognisable and easily accessible place which integrates different transport modes and supplements them with enhanced facilities, services and information aimed at encouraging more sustainable travel, creating sense of place and improving journeys and travel choices”

The SEStran Mobility Hubs Strategic Study states that for a place to be defined as a Mobility Hub, it should meet the following criteria:

- Co-location of public transport and shared transport (at least one or more public transport mode; and one or more shared transport mode);

- Safe and secure bicycle storage;

- A place for everybody (good lighting, visibility, accessibility, and safety);

- The redesign of space (improving the surrounding public realm);

- Serves local needs (residential population, employment, visitors, or multiple user types); and

- Identifies the space as a Mobility Hub through a branded pillar or board and provide travel information, which is clear and visible.

As stated above, for the Hubs to be developed in East Fife, one of the key requirements is to introduce both public and shared transport options in the hubs. Shared mobility options may include bike share, bike hire, e-scooter share (subject to legal approval), car clubs and Digital Demand Responsive Transport (DDRT).

A proposed location for a Mobility Hub in St Andrews does not have shared mobility options at the moment.

### CoMoUK Mobility Hubs accreditation

CoMoUK has developed a set of standards for assessing Mobility Hubs and can provide formal accreditation status at either bronze, silver, or gold standard. Figure 1 summarises the quality standards which each hub should have to be accredited. One of the requirements is also co-location of public and shared mobility modes.

Figure 1. CoMoUK accreditation - six success factors

Source: CoMoUK

## Structure of the document

This document includes the following chapters:

Chapter 2 – Mobility Hub – scheme description by option;

Chapter 3 – Scheme costs by option;

Chapter 4 – Strategic case – policy context and rationale;

Chapter 5 – Economic case;

Chapter 6 – Financial case;

Chapter 7 – Management case – delivery plan and operations;

Chapter 8 – Commercial case –procurement; and

Chapter 9 – Conclusion.

# Mobility Hub assessment

## Overview

This chapter provides a summary of the assessment of a Mobility Hub in St Andrews.

The assessment has been conducted based on the following activities:

- Literature review and analysis of the collected data;

- Review of policy and strategies (national, regional and local);

- Technical assessment of the sites and site visits (see Appendix A);

- Stakeholder engagement; and

- Engagement with Fife Council and SEStran.

## Mobility Hub in St Andrews

### Aims and objectives

In addition to providing a range options for residents, a Mobility Hub in St Andrews can support the current visitor and tourism offer for the University and golfing town, helping to increase the active travel options available, reducing the pressure that high traffic volumes put on the town’s medieval infrastructure and environment.

The key objectives for the hub are based on the main objectives of Mobility Hubs presented in the Strategic Mobility Hubs Study and adjusted to the local context in St Andrews:

- Improve connectivity from the railway network to St Andrews through the integration of transportation options and other services;

- Integrate shared mobility to complement the existing transport network;

- Improve accessibility for those with limited transport choice or no access to a car;

- Support people to make informed travel choices through integration and provision of information;

- Promote inclusivity and follow design standards for disabled people or those with mobility impairments;

- Support low carbon choices and reduction of emissions;

- Increase use of shared mobility as an alternative to the private car and facilitate a shift to more sustainable and active modes to reduce car ownership;

- Encourage behavioural change for residents, workers, students and visitors and facilitate a modal shift to more sustainable modes of transport;

- Ensure safety and security for people using the hub; and

- Create a sense of place and community and reallocate space in the public realm through placemaking and effective land use.

It is proposed that a Mobility Hub is located with services both at St Andrews bus station and within the car park adjacent to the bus station. This location was selected as the bus station is the focus for public transport in the town and is situated in a central location serving both the town centre and University. The hub would be comprised of the elements presented in Table 2. A detailed technical assessment of St Andrews area is presented in Appendix A.

Two Do Something scenarios have been developed for the hub:

Do Something 1 (DS1): this is the central scheme plan, including the “must have” facilities and services; and

Do Something 2 (DS2): this scenario (‘Do Maximum’) includes everything in DS1 and additional “nice to have” services and facilities.

St Andrews bus station is on City Road and is a few minutes’ walk from the town centre. There are four stances for buses to depart in the bus station and one on Station Road (stance 5). The main entrance is on the Station Road/City Road junction. The four stances are accessed from the main building via double doors. There is level access throughout the building and on the stances. The University campus can be easily accessed by foot via Petheram Bridge car park and Station Road (5° incline) or a 150m, 3° inclined path then via a footway and crossing with dropped kerbs to the stances. St Andrews Bus Station is owned and operated by Stagecoach in Fife. Figure 4 below shows the information pillar at St Andrews bus station and Figure 8 shows the free parking facilities near the bus station.

The bus network is crucial in linking St Andrews to the railway network approximately 6km away in Leuchars, and to airports which are further afield St Andrews is linked by a cycle path from the centre of St Andrews to within 500m of Leuchars railway station.

Table 1. St Andrews Mobility Hub

| Existing facilities | Do Something 1 (DS1) | Do Something 2 (DS2) |
| --- | --- | --- |
| Bus station: Secured cycle storage (the bus station has six unsheltered Sheffield hoops and six secure cycle storage lockers - see Figure 3 below) Taxi rank/pick up drop off area Wi-fi Digital pillar with bus information Shop within the station Toilets Left Luggage Waiting room CCTV Cameras | Bike repair stand/bike pump Two EV car club parking bays with a single EV charging station with two charge points Bike share parking bay (for up to 10 vehicles) Parklet/seating facilities Updated digital information pillar Additional signage and wayfinding on the platforms, at the bus stop, at the hub area including tourist information Additional CCTV provision (at the car park) | Public realm improvements (access to car park and link to the city centre) Phone charging facilities |

A description of DS1 additional facilities and services proposed at the Hub is presented below:

Bike share parking bay (for up to 10 vehicles) to form a part of the e-bike share scheme which is in the process of being procured by St Andrews University

- A public bike repair stand provides tools where people need them, offering a free facility for people to make repairs to their bikes;

Two EV car club parking bays with an EV charging station; the cars provide the opportunity to access an EV on an hourly/daily basis with all costs included, and to use a vehicle by those who do not own a car, or want to test an EV;

- Parklet/seating/planting including plants and flower beds to improve the landscape; comfortable and accessible seating; artwork to improve the quality of space (e.g. an opportunity for local artists to contribute to placemaking);

- Digital information pillar with real-time information and journey planning function; the pillar can be also used to provide information on how shared transport modes and other facilities available at the hub can be accessed and used;

- Additional signage and wayfinding: a Mobility Hub should be linked to a local legibility/wayfinding strategy; signage for hiking trails and cycle routes should be provided as part as wayfinding; and

Additional CCTV provision (at the car park).

A potential location for the Hub’s key facilities is presented in Figure 2 below.

Figure 2. A potential location for the Hub’s key facilities

Figure 3. Secure Cycle Lockers, St Andrews Bus Station

Figure 4. St Andrew Bus Station: Information board

Figure 5. St Andrews Bus Station: adjacent car park

# Mobility Hubs costs - by option

## Overview

To determine the costs for implementing a Mobility Hub, the information was collected from a range of relevant available evidence. This includes:

Costs of Mobility Hub implementation shared by London Borough of Redbridge

Costs presented in Mobility Hub Design Guide by Solent Transport; and

Stakeholder engagement with Fife Council, SEStran and St Andrews University.

It is important to note that there are very few Mobility Hubs which have been implemented in the UK, and therefore we have taken a conservative approach to costs, to reduce the potential risk of additional unforeseen costs. The costs have been estimated for two scenarios:

Do Something 1 (DS1): this is the central scheme plan, including the “must have” facilities and services presented in Chapter 2.

Do Something 2 (DS2): this scenario (‘Do Maximum’) includes everything in DS1 and additional “nice to have” services and facilities in Chapter 2.

When planning the Mobility Hub, consideration should not only be given to the project’s capital expenditure (CAPEX) including the design and construction of the new facility but also the ongoing operating expenditure (OPEX). The scheme costs discussed in this chapter have been broadly divided into two sections:

Capital costs; and

Operating costs.

## Capital costs

The capital costs for the Mobility Hub are broken down by element and included supply and installation costs for the different components.

#### Design, procurement, installation, surveys, construction and project management costs

The unit costs presented exclude associated foundations, groundworks and M,E & P services. Design, procurement, installation, construction, required surveys (e.g. topographical surrey) and project management costs.  These costs have been assumed to be 50% of the total price of unit costs (based on the assumptions made in the Solent Transport Mobility Hub Guide).

Staff time from Fife Council/SEStran required for procuring the hubs and implementing them is assumed to form a part of the design, procurement, installation, surveys, construction and project management costs.

#### Contingency Costs

It is important to build in contingency costs into the budget to make allowance at each stage for design development, foreseen risks, unforeseen risks and delays in the programme. As the project develops the percentage of contingency costs can be reduced as the project risks are addressed. The contingency of 20% is applied to the capital costs of the Mobility Hub’s components and design, procurement, installation, project management fees.

Table 2. Capital costs - St Andrews

| Cost element | Capital costs (£, 2021 prices) | Comments | Scenario |
| --- | --- | --- | --- |
| Bike repair stand / bike pump | 2,000 | Based on the market price between £1,000 - £2,000 | DS1 |
| Two EV car club parking bays with a single EV charging station | 7,000 | Includes the price of the dual charging station (more than 20kW) and lines/signs required for the bay | DS1 |
| Bike share parking bay (for up to 10 vehicles) | 1,000 | Lines and signs for the bay | DS1 |
| Parklet/seating facilities | 15,000 | The price of the parklet will depend on the specification and design chosen: the market average is between £10,000 - £25,000 | DS1 |
| Updated digital information pillar | 15,000 | Based on the price paid by the current provider of the digital screens at the bus stops in Fife. Costs vary depending on the style and functionality of the pillar | DS1 |
| Additional signage and wayfinding on the platforms, at the bus stop, at the hub area including tourist information | 15,000 | The price of signage will depend on the specification and design chosen | DS1 |
| Additional CCTV provision (at the car park) | 3,000 |  | DS1 |
| Public realm improvements (access to car park and link to the city centre) | 85,000 | Based on the price of Monastery Street, Dunfermline Streetscape Improvements (March 2018) using Caithness slab. The price will depend on the specification and design chosen | DS2 |
| Phone charging facilities | 2,000 | Can be integrated into the design of the parklet | DS2 |
| Total base costs - DS1 | £58,000 |
| Design, procurement, installation, construction and project management costs (50%) | £29,000 |
| Contingency (20%) | £17,400 |
| Total – DS1 | £104,400 |
| Total base costs – DS2 | £87,000 |
| Design, procurement, installation, construction and project management costs (50%) It should be noted that the main costs of the DS2 scenario are allocated to public realm improvements, which will be determined at procurement stage. As such, allocating 50% on top of the proposed costs could result in artificially increased costs of DS2. | £43,500 |
| Contingency (20%) | £26,100 |
| Total - DS2 (including DS1) | £261,000 |

## Operating costs

It has been assumed that there will not be a variance between operation costs in DS1 or DS2 scenarios. The operations costs will be the same based on the improvements and additional facilities proposed in DS2.

The costs of ongoing management and administration of the facility are assumed to be limited and will not require additional staff to be recruited by Fife Council.

The annual ongoing operating and maintenance (O&M) costs include:

Cleaning and maintenance of the hub space;

Updates and maintenance of the digital screens;

Promotion and marketing;

Monitoring and evaluation; and

Planting/gardening.

The ongoing operating and maintenance costs for the bike share scheme and car club operations are assumed to be covered by the operator.

Table 3. Operating costs – St Andrews Mobility Hub

| Cost element | Operating costs per year (£, 2021 prices) | Comments |
| --- | --- | --- |
| Cleaning and maintenance of the hub | 5,000 | The costs are assumed to be minimal - the cleaning and maintenance could be agreed with Stagecoach operating St Andrews Bus Station or existing cleaning contracts with Fife Council |
| Updates and maintenance of a digital pillar | 5,000 | The costs are assumed to be minimal – the screens could be maintained by the same company which services the existing digital screens at the bus stops in Fife. |
| Promotion and marketing | 15,000 | Year 1 |
| Monitoring and evaluation | 30,000 | Working with operators and conducting surveys - for Year 1 and 2 only (see Chapter 7 for details on monitoring and evaluation) |
| CCTVs monitoring | £0 | Assumed to be added to the existing CCTV operations contract |
| Planting/gardening | 8,000 | The costs are assumed to be minimal - gardening costs could be agreed with Stagecoach operating St Andrews Bus Station or existing gardening contracts with Fife Council |
| Total Year 1 | £63,000 (per year) |
| Total Year 2 | £53,000 (per year) |
| Promotion and Marketing | 5,000 | Year 2 + |
| Total Year 3+ | £23,000 (per year) |

## Managing costs

As stated in the Solent Transport Mobility Hubs Design Guide, to offset both the CAPEX and OPEX costs, thought should be given to how to reduce costs or recoup costs on an ongoing basis to assist the hub with its own financial sustainability. Areas to consider are set out below.

### Capital expenditure

Professional fees may be reduced by employing multidisciplinary design teams (one-stop shop approach) or employing individual professionals who can also provide Project Management or Contract Administration services;

Undertake competitive tendering for both the design and construction phases of the project or utilise framework contractors who have already undergone the competitive tendering process;

The utilisation of the same materials and equipment throughout a suite of hubs will help with economies of scale when purchasing (e.g. in Leven, St Andrews and Leuchars); and

The use of off-site prefabricated or modular buildings will help reduce the time spent on site and help to reduce the construction costs.

### Operating expenditure

The utilisation of the same materials and equipment throughout a suite of hubs could assist in reducing maintenance costs, particularly with regards to training the maintenance team and the provision of spares;

Installing sustainable elements to generate power such as solar panels;

Agreements with ScotRail and Stagecoach to clean/check the hubs space;

Agreements with the existing CCTV operators, digital screen providers for maintenance of the hub’s components; and

Agreements with existing greening /gardening contract.

# Strategic Case – policy rationale and need for intervention

## Overview

This section sets out the policy rationale behind the concept of Mobility Hubs in the SEStran region and demonstrates the case for delivery of the Mobility Hubs in St Andrews.

The structure of the Strategic Case is as follows:

- Policy review: this sets out the national, regional and local context which frames the need for the scheme;

- Evidence base: this draws insights from social, environmental, economic and transport datasets to show that there is a case for changes;

- Need for intervention: this summarises how the policy review and evidence demonstrate that there is sufficient need and a policy context that would support intervention; and

- Option assessment: this sets out the different options for addressing the need for intervention and assesses it against the objectives of intervention.

## Policy review

This section sets out the relevant policies which relate to Mobility Hubs. There are a range of policy and strategy documents that could be reviewed to demonstrate support for Mobility Hubs and improvement of connectivity and sustainable transport options. To ensure the review remains focussed on the proposed Mobility Hubs in East Fife specifically, the policy review is structured around six key objectives (adapted to the objectives developed in the SEStran Mobility Hubs Feasibility study):

- Embracing innovation and shared mobility;

- Improving access to education and employment/ equity and inclusion;

- Reducing emissions;

- Improving health and wellbeing;

- Promoting a stronger economy (through a high-quality and integrated transport system); and

- Resilience from the Covid-19 pandemic.

Our review of each of the six objectives includes a national overview (Scotland), regional overview (SEStran region) and local overview, which includes the local objectives as covered in the adopted Fife Plan 2017.

Table 4 below presents all documents which have been included in the review, though some are more relevant than others, and the relevance of each varies between the six objectives.

Table 4. Policy and strategy documents included in the policy review

National

Transport (Scotland) Act 2019 The Climate Change (Scotland) Act 2019 National Transport Strategy (NTS) 2, 2020 Securing a green recovery on a path to net zero: climate change plan 2018–2032 Cycling Action Plan for Scotland, 2017-2020 Strategic Transport Projects Review (STPR2) – Phase 1 Transport Scotland Active Travel Framework

Regional

SEStran Regional Transport Strategy (RTS) – Case for Change, 2021 SEStran Mobility Hubs Strategic Study SEStran strategic network Adopted Fife Local Development Plan, 2017 Fife’s Local Transport Strategy (2006 – 2026) Fife Council Capital Strategy, 2019 – 2029

Local

St Andrews & East Fife Local Plan, Adopted October 2012 University of St Andrews, Strategic Transport and Travel Plan (STTP) 2020 - 2025 University of St Andrews Strategy 2018 - 2023.

### Embracing innovation and shared mobility

#### National

The National Transport Strategy 2, 2020 (NTS2) recognises the use of innovation, pioneering new products, services and technologies. There is a commitment to secure opportunities and investment for innovation and growth of testing platforms and supply chains. In addition, Transport Scotland’s Strategy aims to use innovation and technological advances to facilitate sustainable transport modes, provide greater and equal opportunities for disadvantaged groups and increase the overall efficiency and safety of the transport system.

Scottish Government’s Securing a Green Recovery on a Path to Net Zero, similar to NTS2, recognises the importance of innovation in meeting climate change targets, with a focus on promoting Ultra Low Emission Vehicles (ULEVs) uptake through planned investment in the supporting technology. The Scottish Government also mentioned that they are harnessing innovation within the transport system by investing up to £2 million through MaaS Investment Fund (MIF) over three years to develop Mobility as a Service (MaaS) in Scotland, along with investment in innovation to promote uptake of ULEVs. There will also be investment into innovations in logistics, particularly in response to the increase in e-commerce activity.

In the Cycling Action Plan for Scotland, Transport Scotland details seven innovative projects in both infrastructure and behaviour change, where they work in partnership with key stakeholders to encourage more people to cycle.

The Transport Scotland Active Travel Framework summarises the key policy approaches to improving the uptake of walking and cycling in Scotland for travel. At its heart is an ambition that by 2030, Scotland’s communities are shaped around people and place, enabling walking and cycling to be the most popular mode of travel for short, everyday journeys.

In the STPR2, strategic options that are considered include demand management measures, which make use of technology, innovation and behavioural change. There is a recommendation that capital funding should be focused on pilot schemes that draw on innovative solutions, supported by MaaS/ smart technology, or international best practice in bus service provision.

#### Regional

Transport Innovation is identified as one of three factors that have been taken into consideration when developing the SEStran Regional Transport Strategy (RTS). The four main areas of transport innovation are Alternative Fuels, Shared Mobility, Mobility as a Service (MaaS) and Automation.

In the SEStran Mobility Hubs Strategic Study, “Embracing Innovation” includes integrating new transport innovation with existing services and providing an opportunity to test innovative technologies and support early adoption of beneficial transport innovations. Mobility Hubs are also considered to be physical enablers of MaaS.

#### Local

In the University of St Andrews Strategy, the University commit innovation in their approach to supporting teaching, research, outreach and impact. They also aim to create opportunities for investors, industry and policy makers through innovative thinking that will help to assemble disruptive ideas and overcome major challenges.

The Scottish Government committed to a £2 million investment fund in 2018, over three years, to support the testing of the Mobility as a Service (MaaS) concept in Scotland known as MaaS Investment Fund (MIF). The programme aims to test and pilot integrated transport options in real-time situations and evaluate viability of MaaS in Scotland. The objective of the programme is to provide people with easy, digital access to travel information so they can be better informed as to the different ways to undertake their journey. A project funded by MIF focusses on piloting innovative solutions using new and existing transportation modes, digital tools (Apps), physical infrastructure, programs, and interventions that improve connections to and from St Andrews to Scotland’s major settlements.

### Improving access to education and employment/ equity and inclusion

#### National

The Transport (Scotland) Act 2019 mentions matters that must be improved, including social inclusion, inclusion of the elderly and persons with disabilities, inclusive economic growth, reduction of poverty and inequality, and access to further education via public transport. The Climate Change (Scotland) Act 2019 seeks to contribute to resource efficient and sustainable economic approaches which help to address inequality and poverty.

In the NTS2, another priority area is inclusive economic growth where people have fair and affordable access to the jobs where they can be most productive, as well as are able to access education and training. Of particular interest is understanding women’s travel behaviour so that their access to employment and educational opportunities can be prioritised.

In Securing a Green Recovery on a Path to Net Zero, the importance of equity is discussed, with improvements in bus infrastructure given as an example of a measure that will improve connectivity for people in lower socio-economic groups.

In the Cycling Action Plan for Scotland, Transport Scotland aims to increase the levels of access to bikes through projects that support inclusive cycling initiatives such as through Cycling Scotland’s Cycle Friendly and Sustainable Communities Fund. They also aim to work collaboratively across all policy areas to promote cycling and increase participation for young people of all abilities.

The Transport Scotland Active Travel Framework’s intention is that travelling by foot or cycle is a realistic option for all local journeys as individuals. It also aims to ensure people are confident to walk and cycle more often and they value and use their local transport networks (streets, roads and path networks), which offer safe, high quality, realistic and predictable journey options for active travel.

STPR2 states that in the last decade, there has not been a sustained impact on the increase in walking and cycling, particularly as a means to travel to work or education, but that in recent years, the Scottish Government has committed significant investment into active travel to help address this issue. Five Transport Planning Objectives (TPOs) were developed, which included having “an inclusive strategic transport system that improves the affordability and accessibility of public transport”, thus reducing transport poverty, improving mobility and inclusion and reducing the reliance on private car for access to key centres for healthcare, employment and education. Another TPO was “an integrated strategic transport system that contributes towards sustainable inclusive growth in Scotland”, which included increasing sustainable access to labour markets and key centres for employment, education and training.

One of the proposed interventions in the STPR2, which was around development of Glasgow “Metro” and Edinburgh Mass Transit strategies, highlighted that the various corridors should focus on improving access to key hubs such as the city centre, hospitals, major education facilities, key employment centres and other services.

#### Regional

One of the transport problems listed in the RTS was that some journeys cannot be made by public transport. Connectivity and Deprivation Audit Tool (CDAT) analysis was done to identify locations that suffer from deprivation and poor public transport connectivity to education, healthcare and employment. The RTS recognises that shared mobility trends could potentially deliver mobility lifestyles that are more inclusive than traditional travel systems, as well as  help in delivery of inclusive economic growth alongside reducing carbon emissions. The importance of integration between land-use and transport planning is also discussed, as this will create growth opportunities and can also ensure sustainability and inclusivity through equitable access.

In the SEStran Mobility Hubs Strategic Study, stakeholder engagement included engaging with local authorities due to their role in improving access to employment, education, healthcare and other services. One of the key objectives of Mobility Hubs in the SEStran region is improving accessibility, where inclusivity is promoted, and design standards followed for disabled people or those with mobility impairments. It also covers improving accessibility for those with limited transport choices or no access to a car.

The SEStran Strategic Network report mentions that a stakeholder workshop was held in January 2020 to plan the cycling and walking network. The report includes maps identifying key barriers to active travel, existing infrastructure and emerging proposals for a strategic active travel network. This travel network included desired links to rail stations; links between settlements with shared services such as community, health, retail, education; links to new development; and links along key commuter routes linking to key employment zones and education.

In the Fife Council Capital Strategy, two of the four priority themes which will direct their work over the next ten years are Opportunities for All and Inclusive Growth and Jobs. Following the former theme, Fife Council aims to ensure that everyone in Fife can access opportunities in education, training, jobs and wider society. Under Inclusive Growth and Jobs, it is highlighted that growth in the local economy should benefit everyone by improving investment, growth and participation by businesses, people and communities.

#### Local

The St Andrews & East Fife Local Plan identifies that, given East Fife has an older population profile, there is a need to plan ahead and deliver solutions for this user group to ensure social services such as education and healthcare are accessible to Fife residents.

The University of St Andrews, Strategic Transport and Travel Plan 2020 – 2025 (STTP), reiterates the objectives of the NTS2, saying that Scotland’s transport system will be sustainable, inclusive and accessible, and cites the four priorities, which include promoting equality, helping the economy prosper and improving health and wellbeing. The University Plan also cites the Equality Act 2010, which aims to prevent disability discrimination and provide legal rights for disabled people including access to land-based transport services, and Inclusive Mobility Guidance which mainly protects disabled people (and other people with small children or heavy luggage) and helps them to benefit from good design of the pedestrian and transport environment.

### Reducing emissions

#### National

The Transport (Scotland) Act 2019 states that any national transport strategy that is prepared must consider the environment, particularly the meeting of emission reduction targets and also makes provision for low emission zones (LEZs). The Act states that Scottish Ministers may make grants to a person to help them meeting the costs of making alterations to a vehicle in order to reduce its emissions.

The Climate Change (Scotland) Act 2019 aims to set targets for the reduction of greenhouse gas emissions, with Scotland contributing to the world’s efforts to deliver on the Paris Agreement at the 21st Conference of the Parties of the UNFCCC.

The NTS2 states that the Scottish Government has committed to achieve net-zero greenhouse gas emissions by 2045. It cites the Climate Change Act passed by Scottish Parliament which aims to reduce greenhouse gas emissions to 75% of 1990 levels by 2030, 90% by 2040 and achieve net-zero by 2045. Transport is identified as the largest contributor to Scottish emissions and the Government therefore seeks to reduce emissions from transport by phasing out petrol and diesel vehicles from the public sector fleet by 2025 and phasing out the need for new petrol and diesel cars and vans in Scotland by 2032. They also  plan to design the transport system so that walking, cycling and public and shared transport take precedence ahead of private car use.

The Securing a Green Recovery on a Path to Net Zero, which focuses on the period up to 2032, recognises the role of public and private investment as essential for transitioning to net zero. There is a commitment to delivering a place-based approach where concepts such as a 20-minute neighbourhood will prioritise quality of life and health as well as net zero ambitions.

STPR2 objectives also include having a sustainable strategic transport system that contributes significantly to the Government’s net zero emissions target, as defined in the NTS2.

#### Regional

In the RTS, alternative fuels are explored, as well as Shared Mobility and Automation to reduce emissions. Within the Shared Mobility theme, it is envisioned that shared mobility transport options are used in an integrated manner through creation of Mobility Hubs.

The Mobility Hubs Strategic Study highlights that the primary objective for Mobility Hubs include supporting low carbon travel choices and reducing emissions, as well as encouraging a behavioural change that will facilitate a modal shift to more sustainable modes of transport including walking and cycling. Furthermore, Mobility Hubs can promote greener choices through provision of EV charging infrastructure, storage facilities for bicycles and provision of first and last mile travel through car club and bike share.

SEStran Strategic Network considers carbon emissions as part of the economic assessment of the strategic network and the effect of emissions reductions on living environments and air quality.

The Fife Council Capital Strategy commits to decarbonisation of the road transport fleet by 2050, in line with Scottish Government commitments. Fife Council also aims to move away from travel by car towards cycling and walking supporting carbon reduction.

The Adopted Fife Plan considers sites’ potential to be low carbon development and encourages them to contribute to low carbon principles using placemaking, design, use of greenspace, and locations which take advantage of the transport network to reduce unnecessary travel.

#### Local

The St Andrews & East Fife Local Plan provides a framework for the shift to more sustainable modes of transport which deals with reducing emissions from transport sources. The plan also expects developers to provide for pedestrian and cycle movement, and link footpaths and cycleways to housing, employment and commercial and leisure areas.

The University of St Andrews, Strategic Transport and Travel Plan 2020 – 2025 aims to reduce emissions from transport associated with the operation of the University Estate. The University will also prepare a Business Travel Policy/Hierarchy that suggests that staff consider certain characteristics related to the mode of travel they select, with emissions being a key focus. ChargePlace Scotland Funding is mentioned as a grant that promotes a switch to electric vehicles, thus reducing emissions.

The main aim of the MIF funded project at St Andrews University is to improve travel experience, facilitate trip chain options and enable people to leave their car at home confidently. It will also show how  integration of multiple MaaS Apps and services can prioritise low carbon modes and quantify emissions per trip.

### Improving health and wellbeing

#### National

Several national policy and strategy papers list health and wellbeing as an important objective. The Transport (Scotland) Act 2019 lists health and wellbeing as one of the matters that must be improved, along with social and economic wellbeing. The Climate Change (Scotland) Act 2019 recognises that any target-setting criteria should include the likely impact of the target on public health.

In the NTS2, the vision for Scotland’s transport system includes improving health and wellbeing. This will be done by facilitating people to make active travel choices that will improve health and physical and mental wellbeing. It stresses that the transport system should support public health priorities. In addition to this, the transport system should aim to reduce levels of social isolation, potentially by including transport choices for people with no access to a car in areas with poor public transport connectivity. The STPR2 also looks to improve health and wellbeing.

In Securing a Green Recovery on a Path to Net Zero, 20-minute neighbourhoods are discussed with an aim to prioritise quality of life and health.

The Cycling Action Plan for Scotland promotes active travel, which will improve health and wellbeing of people in Scotland. Specific actions are proposed to promote cycling and encourage behaviour change, including working collaboratively across all policy areas.

#### Regional

The RTS highlights that access to healthcare is a critical requirement, especially as the elderly population increases. Electric vehicles are also mentioned as providing the social benefits of less noise and air pollution, which leads to better health. Furthermore, one of the main strategic objectives of the SEStran region, as included in the RTS, is to facilitate greater physical activity, which improves health and wellbeing. Similarly, SEStran’s Mobility Hubs Strategic Study states that Mobility Hubs should  improve health and wellbeing through integrating and promoting active travel options, as well as improve access to healthcare services.

The Fife Council Capital Strategy presents a concept or theme of ‘Thriving Places’ as places which are safe and well-designed and promote wellbeing and where people have access to the services and facilities they need at different stages of their lives.

#### Local

The St Andrews & East Fife Local Plan also considers the different stages of life, saying that it is important to plan ahead considering anticipated needs in social services such as education and healthcare. Sport and physical recreation are identified as key elements in maintaining and enhancing a healthy lifestyle.

The STTP, focusses on improving staff health and reducing stress related to travelling, and health promotion due to physical exercise like walking and cycling. It also considers the aims of the NTS2, including improving health and wellbeing. Students are encouraged to use bikes to travel, saving money on public transport and living a healthier lifestyle. The St Andrews University is expected to pursue Places for Everyone funding, which aims to create safe, attractive and healthier places by increasing the number of trips made by walking, cycling and wheeling for everyday journeys.

### Promoting a stronger economy (through a high-quality and integrated transport system)

#### National

In the NTS2, the transport system is identified as playing a crucial role in the successful performance of Scotland’s economy and ensuring regional cohesion. The transport system contributes to Scotland’s competitiveness, impacts on productivity and the efficiency of businesses. Several policies are listed that help to realise inclusive economic growth, such as increasing the resilience of Scotland’s transport system from disruption and integrating transport and wider infrastructure policies and investments in order to unlock greater benefits. It highlights that the transport system should aim to integrate network and services with spatial and land use planning, and there should be better integrated decision making – both between transport and individual sectors such as energy and digital, as well as within the wider Scottish Government infrastructure investment process.

STPR2 presents a series of Transport Planning Objectives (TPOs), with one of the sub-objectives being increasing public transport mode share by connecting sustainable modes of transport to facilitate integrated journeys. In addition to this, a suggested intervention is providing infrastructure at rail stations that facilitates access for all, where opportunities to improve integrated journeys at stations are identified, e.g. by reviewing onward accessibility particularly by bus and taxi.

#### Regional

The four main areas of transport innovation that are relevant to the RTS include MaaS and integrated transport and shared mobility, which could be supported through development of Mobility Hubs.

The Mobility Hubs Strategic Study presents key objectives of the economy, which are to improve connectivity through the integration of transportation options and other services, as well as to integrated shared mobility to complement the existing transport network.

In the Fife Council Capital Strategy, it is emphasised that Fife’s roads and transportation infrastructure is critical to supporting the daily lives of its communities by delivering a thriving economy and contributing to Fife’s connectivity and built environment. It is a statutory duty to have effective asset management and maintenance of this infrastructure.

#### Local

The St Andrews & East Fife Local Plan notes that it is important to attract inward investment to support and strengthen the rural economy. The East Area Transport Plan is mentioned, with improved public transport provision being integral to the document, including development of the Leuchars railway station and improved integrated public transport feeder services between St Andrews and Leuchars railway station.

The STTP mentions the TAYplan Strategic Development Plan 2016 – 2036, which states that transport and land should be integrated to:

- Reduce the need to travel and improve accessibility by foot, cycle and public transport;

- Make the best use of existing infrastructure to achieve active travel;

- Support land use and transport integration by transport assessments and travel plans where appropriate.

The STTP also mentions Fife’s Local Transport Strategy 2006 – 2026, which seeks to achieve the main objectives formed by the Scottish Government regarding integration of the transport network. The University also explores the concept of a Smart Campus, where MaaS encourages a shift away from personally owned modes of transport. MaaS is considered to include high quality bus and rail services, car share schemes, demand responsive transit, cycle hire and electric-cycle hire, car rental services and rental packages.

### Resilience from the Covid-19 pandemic

#### National

In Securing a Green Recovery on a Path to Net Zero, the Scottish Government pledges to make a Green Recovery from the Covid-19 pandemic and embed resilience and security into the society and economy. The Government acknowledges that Covid-19 demonstrated the risks of abrupt, unplanned shifts and exacerbated inequalities in society. However, they see a green recovery as something that offers opportunities to address these inequalities. Although there are fiscal challenges due to the Covid-19 crisis, the Scottish Government have continued to prioritise action to reduce emissions from transport. There were positive behaviour changes during the Covid-19 pandemic that the Government aims to maintain, such as an uptake in active travel and conversely, less flights, both of which resulted in reductions in emissions and air quality improvements. The Government’s Infrastructure Investment Plan would play a role in recovering from the economic, health and social harm that arose from the Covid-19 pandemic, across different sectors, including transport.

In STPR2, Phase 1 draft recommendations for investment by Transport Scotland requires meeting criteria such as “will support a fair and sustainable economic recovery following the Covid-19 pandemic and help lock in the sustainable travel behaviours observed during lockdown and contribute to addressing the increasing car dependence and low public transport usage.” It also highlights that while there has been a positive shift towards active travel due to the Covid-19 pandemic, there was conversely also a significant drop in demand for public transport. Thus, it is important that STPR2 addresses the NTS2 vision of providing attractive, affordable and accessible sustainable travel options

#### Regional

The RTS also recognises the long-term trends in travel behaviour because of the Covid-19 pandemic. One example given is that people may be less willing to ride share with strangers while the virus remains a threat. The RTS reports that SEStran has been running a Travel Attitudes Survey throughout the pandemic which is tracking various changes in travel behaviour due to the Covid-19 pandemic.

#### Local

The Spaces for People interventions in St Andrews were implemented at the beginning of October 2020. The aim was to provide pedestrians with more space on the streets. Five locations in St Andrews – Bell Street, Church Street, Market Street, South Street East and South Street West – extended the pedestrian areas into the carriageway by up to 2.5m.

## Evidence Base

### Embracing innovation

Connectivity and easy access to services helps economy to thrive. With the advancements in technology and increased access to smart phones, shared mobility solutions such as bike share and car clubs have been successful in recent years in complementing or replacing trips made by other modes, particularly providing a solution for first/last mile travel where traditional public transport has struggled.

The small-scale shared e-bike hire scheme ‘Go E-bike’ launched in 2018 at St Andrews University with e-bikes for staff have been successful to encourage staff in making short distance trips between the campuses and the town centre. The scheme has 34 users, with 13 regular users. Over 550 trips have been made during the first four months of operation in 2019 (pre covid-19). With plans to expand the scheme further, it is expected that more car trips made by University staff can be replaced.

Bringing shared mobility and public transport modes together increases the collective appeal of the services and enables seamless access to different transport choices providing an attractive alternative to private car travel and helping tackle congestion and air quality issues in the area.

As an example, the city of Bremen which has over 40 Mobility Hubs of different sizes has removed over 6,000 cars off road and has seen a higher reduction in traffic compared to other German cities which is attributed in part to its policy of having different sustainable transport choices such as shared bikes and cycle parking at the same hub as car clubs.

In the city of Austin USA, a new community Mobility Hub was introduced to improve integration where residents drove private cars to the public transport nodes. After the introduction of shared mobility and placemaking improvements around the hub, respondents walked more and drove less. Walk trips increased by 25%, dwell times increased by 144% and self-reported car mode-share decreased by 39% which demonstrates increased health benefits associated with using active modes more frequently as well as economic benefits from higher dwell time leading to more use of local facilities, cafes and shops. Data also suggested that trips using e-scooters and bikes have replaced more car trips than public transport or walking trips.

Alongside offering alternative options to reduce private car travel, availability of innovative non-mobility services such as information pillars, parcel lockers, wi-fi, cafes and shops creates an attractive public place and enhances the quality of life in locations which would otherwise have been used as a car park. The Hubs for Hello Bikeshare scheme in Amsterdam demonstrated that the stations with a clear sign and user-information (via a pillar) had around 28% more users than stations with no branding or information.

Mobility Hubs can bring together traditional and innovative mobility and non-mobility services in a visible and easily recognisable places that increase awareness of alternative travel choices and useful services and encourage higher usage by residents and visitors alike.

### Improving accessibility/ equity and inclusion

Mobility Hubs often utilise space that would otherwise be used for car parking. The City of Vienna’s Mobility Hubs Guidance suggests that planning Mobility hubs as part of new developments can enable reduced parking requirements which in turn can reduce the cost to a developer by around 8.5% for a 70m apartment.

With lower car ownership due to availability of Mobility Hubs, the demand for parking can be reduced over time and on-street space can be repurposed for better access for people with disabilities, with more pedestrian space, safe crossings and other visual enhancements.

In addition, availability of different transport choices at a Mobility Hub improves first and last mile connectivity particularly for users without an access to a car and increases access to education and/or employment therefore assisting with the objectives of improving accessibility of transport services.

App based services disproportionately benefit smart phone users. The physical availability of real time travel or tourism information, ticketing facilities and other non-mobility services can further help bridge the gap in access to services between technology users and non-users.

### Reducing emissions

In the old urban area of Møhlenpris, City of Bergen, Norway which is currently being developed as a car-free neighbourhood, three new Mobility Hubs have led to a significant decrease in private car ownership of 30% over two years. Also, the usage of car sharing in Bergen increased sharply after the introduction of Mobility Hubs in 2019 by about 72%.

In the city of Bremen, which offers car club cars at its Mobility Hubs, a study in 2018 found that each car club car replaced an average 16 private cars. It also found that the kilometres travelled by a car club household is 50% lower than an average household in Bremen which is more likely to consider non-car travel choices available and uses shared modes more often.

Cycling offers a zero-emission travel alternative with relatively competitive journey times in an urban/semi-urban context when compared to both private cars and public transport, both of which contribute to the UK’s transport emissions. The 2020 Scottish CoMoUK annual bike share user survey results revealed that 27% of bike share users would have made their last trip by car or taxis if bike share would not have been available. Further, 41% of respondents have mentioned that they reduced their car use as a result of the availability of bike share schemes.

Therefore, availability of bike share/rental services at the Mobility Hubs would actively encourage such mode shifts contributing to reductions in carbon emissions and supporting the net-zero emissions target.

Pure EVs are zero polluting vehicles compared to an average UK car that emits 150g of CO2 per km. The 2016 Public attitudes to EVs survey by DfT found that 82% of driving licence holders in the UK think reliability of charging network is an important factor for EV purchase. Therefore, availability of EV charge points at visible locations such as Mobility Hubs can support car owners with transition to EVs.  This will also allow car club providers to include EVs in their fleet at the Hubs.

Mobility Hubs have the potential to positively contribute to climate and air pollution targets by reducing the number of vehicles/cars on roads, lowering use and car ownership rates among users, and supporting the shift of trips to environmentally friendly modes of transport such as cycling.

### Improving health and wellbeing

An active lifestyle is considered to be one of the key determinants of health among other factors. The active mode choices such as bike share or bike hire offered at the Mobility Hubs could encourage people to cycle more for both commuting and leisure purposes.

The Scotland CoMoUK bike share surveys consistently found that bike share is a catalyst for getting people cycling. In 2020, 59% of bike share users said that it was the trigger to get them cycling again. Several other health benefits were identified in the survey which include:

- 66% reported exercise/health benefits from cycling (bike share); and

- 41% reported cycling have boosted their mental health (particularly during the pandemic).

Availability of secured cycle parking alongside servicing tools and equipment at the Mobility Hubs can encourage more people to cycle their first and last mile of the journey as compared to using private cars (which are generally parked at monitored/secured car parks) promoting health and wellbeing.

### Promoting a stronger economy

Mobility Hubs can support stronger economic growth through increased access to employment and education, particularly using sustainable modes. Evidence from the Mobility Hubs in Bremen suggest that Mobility Hubs lower congestion and parking issues through less people choosing to drive to work and reduced car ownership amongst car club users.

By improving connectivity through the integration of transportation options and other services, Mobility Hubs help balance supply and demand across a range of sustainable transport options, boosting utilisation and reducing costs. They also present further economic opportunities with some hubs attracting new shops and commercial ventures as more people starting to use them.

In addition, there are wider benefits in terms of increased productivity and quality of life owning to reduced congestion, improved air quality, higher use of shared and active transport and public realm improvements which positively support the case for Mobility Hubs in promoting a stronger economic growth.

### Resilience from the Covid-19 pandemic

Mobility Hubs encourage use of sustainable transport modes, such as bikes, shared bikes, public transport and shared cars. During the Covid-19 pandemic, with the heightened safety concerns about using public transport or other forms of shared transport, popularity and usage of micromobility modes grew significantly as they are perceived as a safer and socially distanced mode of travel, alongside being an alternative to car travel for short distance trips.

The 2020 Bike Share Users Survey by CoMoUK states that 23% of respondents said that the lockdown and restrictions to public transport use led them to sign up for or restart using their local bike share scheme.

The figures released by Transport for London (TfL) show that demand for Cycle Hire in London during the Covid-19 pandemic period has remained high. New 24-hour Santander Cycles membership registrations rose by 167 per cent in the year to December 2020, representing the largest increase in the scheme's 10-year history. Meanwhile, registrations for new annual memberships increased by 25%. Steer has analysed TfL’s open data for Cycle Hire comparing trips from January-May 2019 to January-May 2020. The data shows that despite limited commute trips and the lockdown restrictions in place, demand for Cycle Hire trips was higher in May 2020 than in May 2019. Also, the average Cycle Hire trip duration in London more than doubled from 20 mins in May 2019 to 42 minutes in May 2020.

The effects of the Covid-19 pandemic alongside provision of temporary cycle lanes through the Spaces for People initiative have encouraged people to cycle more across Scotland. Data shows that the number of cyclists increased every month across Scotland in 2020. Moreover, there are discussions on making the changes such as pop-up cycle lanes and wider pavements brought through the Spaces for People initiative in Glasgow permanent based on their positive impacts on sustainable travel choices and climate change goals. There are similar plans discussed in the SEStran region: in Spring 2021, the City of Edinburgh Council ran a consultation on retaining the Spaces for People measures.

Mobility Hubs supporting shared micromobility schemes can lead to a positive behavioural change towards use of micromobility supporting long term sustainability goals.

## Need for intervention – St Andrews

St Andrews is a university town where St Andrews University has around 10,000 students and is also the main employer in the area. St Andrews is also popular tourist destination with more than 675,000 tourists visiting the town per a year pre Covid-19 pandemic. The total population of St Andres is 17,580 (2016 est.).

Driving is the most popular mode of transport for commuting in St Andrews Central at 49%, with areas outside of the main centres having a higher car mode share. Walking is the second most popular mode of commute at 32% with majority of the residents in the north and east of the town center walking to work.

The proposed Mobility Hub at the St Andrews Bus station is planned to improve transport connections and provide alternative modes of travel for residents, visitors and the student population.

About 15,000 St Andrews residents live within five minutes cycling distance from the proposed location and almost the entire population is located within 20-min cycling distance to the St Andrews bus station. This means that providing bike share options at the bus station would allow for car trips to be replaced by a combination of cycling and public transport.

The St Andrews Bike Share Feasibility Study 2019 highlights that ‘many residents state they would replace their current personal car use with a public bike share if one were available and convenient for them, this would ease congestion in the centre of town and open up parking spaces. Long term access to the centre of the town without a car could reduce the need for cars in the centre of town entirely’. Figure 6 below summarises the findings from the survey showing what modes the bike share scheme is likely to replace, with car being identified as the most common mode followed by walking.

Figure 6: Residents replacement transport (to proposed bike share)

Source: St Andrews Bike Share Feasibility Study 2019

Through user research, the study also found that people who are employed in St Andrews but are not residents (approx. 12,000 persons) would like to have a bike share location in transport interchanges such as the St Andrews Bus Station to be able to use the scheme. This clearly demonstrates the potential demand that exists in the area for a Mobility Hub, which can potentially reduce car dependence by improving first and last mile connectivity if it’s provided to serve key destinations and origins across the urban area and available for an attractive fee.

According to the Strategic Transport and Travel Plan 2020-2025 for the University of St Andrews, it plans to secure growth the number of students by 2025, which will require provision of smart and sustainable travel choices that will help meet the University’s commitment to sustainability including reduction of emissions associated with transport.

The proposed Mobility Hub (which is within 5-10 mins walking distance to the University campuses) could potentially positively help address its existing and increasing travel needs by staff, students, visitors and travel needs associated with business activity and services.  As identified in the STTP, central to this will be extending travel choices, developing services, and promoting changes that will offer improved accessibility, and deliver environment, place and community benefits.

The 2019 staff travel survey by the University revealed that the primary mode of journey to work amongst staff is car, with 68% mode share in 2019. Moreover, this is an increase from 2015 levels when car mode share was 60%. Over these five years, bus, cycling and walking mode share have all declined from 37% in 2015 to 27% in 2019. This necessitates the need to provide solutions that would lead to positive mode shift.

20% of staff who travel to work by car said that they choose to do so due to lack of alternative travel options. The 2019 staff travel survey revealed that a large number of staff who normally drive alone use the bus occasionally showing that this is a realistic alternative option for some staff. Also, staff that use the bus rarely spend more than 20 minutes walking from their bus stop to their workplace. Therefore, provision of alternative transport choices for last and first mile trips at bus interchange e.g. bike hire could support positive mode shift.

While there are already some shared mobility choices available at the University such as Go e-Bike scheme, as well as a staff car sharing scheme, a visible and self-promoted Mobility Hub with a dedicated space bringing all the services together will help increase the awareness of the services, and encourage more people, including staff, students and visitors, to replace car trips with shared transport options.

E-Car club was present in St Andrews until October 2019 with operations overseen by St Andrews University. The club consisted of ten electric vehicles which served the university’s staff and students but were not easily available for the residents and visitors to St Andrews with all cars located on University land. Analysis of Scotland’s car club market, funded by Carplus through the Developing Car Clubs in Scotland (DCCS) programme in 2011, identified St Andrews as one of the top five small urban areas in Scotland in which to develop a car club. University of St Andrews MaaSterplan was awarded MaaS Fund Round 2 funding in 2021, for a pilot to promote community-centred mobility services that will tackle issues such as congestion and achieving the transition to net zero, promoting sustainable, active and shared transport options. An EV Car Club is part of the proposals and it is expected that the University will procure a car club operator.

Table 5 which follows summarises how a Mobility Hub at or near the St Andrews University can help meet the policy objectives and demonstrates the need for proposed intervention.

Table 5. Operating costs – St Andrews Mobility Hub

| Objective | Mobility Hub benefits | Potential impact ratings |
| --- | --- | --- |
| Embracing innovation and shared mobility | Availability of shared modes alongside public transport facilitates supports the use of innovative transport solutions improving transport connectivity. Provision of connected services outside mobility services such as information pillar, car clubs, bike share, wi-fi, will support and promote innovation. | High |
| Improving accessibility/ equity and inclusion | Availability of an EV car club and a bike share scheme will provide residents, visitors, employees, and students with better connectivity and encourage modal shift from the private car. Also, given relatively low levels of car ownership (based on high student population rate), this will improve transport choices/connectivity for people who currently do not own a car. | Medium |
| Reducing emissions | Reduction in car trips owing to better first and last mile connectivity to public transport (e.g. bus) and provision of alternative modes such as car club and bike share which support replacement of car trips will help reduce carbon emissions. Some of these benefits have been quantified in the economic case below. | High |
| Improving health and wellbeing | As evidenced, availability of shared mobility will encourage people to walk and cycle more, which in turn will have positive health benefits and improve quality of life. Some of these benefits have been quantified in the economic case below. | High |
| Promoting a stronger economy | A Mobility Hub will support provision of an integrated transport system in the area. Also, increased visibility of the Hub through promotion of services and facilities could encourage higher patronage of bus services in the area, thereby increasing access to work or education or local facilities by non-car modes. | Medium |
| Resilience from the Covid-19 pandemic | The Mobility Hub will further encourage sustainable behavioural change towards shared modes, particularly towards micromobility. | Medium |

# Economic Case

## Overview

The appraisal of the scheme assesses the costs and benefits of a Do Something / With Scheme scenario against a Do Minimum / Without scheme scenario. In this case, the Do Minimum includes the planned improvements in the area, which will take place with and without the scheme.

In this appraisal, two Do Something scenarios have been assessed.

Do Something 1 (DS1): this is the central scheme plan, including the “must have” facilities and services, described in Chapter 2.

Do Something 2 (DS2): this scenario (‘Do Maximum’) includes everything in DS1 and additional “nice to have” services and facilities.

## Scheme costs

### Capital costs

#### Base capital costs

Capital costs for each element of the appraisal are listed in Chapter 3 and have been developed based on several sources, including:

Costs of Mobility Hub implementation shared by London Borough of Redbridge

Costs presented in Mobility Hub Design Guide by Solent Transport; and

Stakeholder engagement with Fife Council, SEStran and St Andrews University.

#### Capital costs for appraisal

For the purposes of the economic appraisal, several adjustments have been made in line with guidance.

Uplift of 50% to account for design, procurement, installation and project management costs.

Uplift of 20% to account for contingency.

In TAG guidance (Unit A1.2), it is assumed that the optimism bias in the Economic Case is applied to the estimated base costs of the scheme, which do not include adjustments for risk or uncertainty. Table 6 replicates Table 8 from TAG Unit A1.2, which shows the recommended optimism bias uplift based on the category, type and stage of a project.

While the scheme does not exactly match any of the categories on the table, it has been decided to use the ‘Roads’ category, as the typology of project is the closest to the current scheme of those listed in the guidance. The optimism bias uplift for Stage 1, which is the corresponding stage for an SOBC for a public transport scheme, is 46%.

Table 6. TAG A1.2 - Optimism Bias recommendation

| Table 8 Recommended optimism bias uplifts for different projects at different stages of the life of a transport project |
| --- |
| Category | Types of projects | Stage 1 | Stage 2 | Stage 3 |
| Roads | Motorway, trunk roads, local roads | 46% | 23% | 20% |
| Rail | Metro, Light rail, Guided buses on tracks, line upgrades, high-speed rail | 56% | 33% | 30% |
| Fixed links | Bridges and Tunnels | 55% | 32% | 28% |
| Building projects | Stations and Terminal buildings | 70% | 48% | 44% |
| IT Projects | IT system development | 69% | 50% | 42% |
| Land and property | Property purchases | 33% | 14% | 0% |
| Rolling stock | Powered and unpowered vehicles | 61% | 38% | 35% |

As explained earlier, the optimism bias uplift figure provided in the guidance applies to the base capital costs. As the capital cost estimates set out in previous sections already include a 20% uplift for contingency, the additional optimism bias uplift applied on top of this is 21.7%. The combination of both uplifts results in a total uplift of 46% on the unadjusted base costs.

The total costs for the Do Something 1 and Do Something 2 scenarios are presented in the tables below.

Table 7. Capital costs incl. optimism bias – Do Something 1

| Capital cost (£, 2021 prices) | St Andrews |
| --- | --- |
| Base cost | 58,000 |
| Design, management, procurement, installation | 29,000 |
| Contingency @ 20% | 17,400 |
| Total base capital cost | 104,400 |
| Optimism bias @ 21.7% | 22,620 |
| Total | 127,020 |

Table 8. Capital costs incl. optimism bias – Do Something 2 (including DS1)

| Capital cost (DS1+DS2) (£, 2021 prices) | St Andrews |
| --- | --- |
| Base cost | 145,000 |
| Design, management, procurement, installation | 72,500 |
| Contingency @ 20% | 43,500 |
| Total base capital cost | 261,000 |
| Optimism bias @ 21.7% | 56,550 |
| Total | 317,550 |

Within the appraisal, the scheme delivery is assumed to be implemented by 2023, with capital costs incurred in the year before the scheme opens, in 2022.

### Operating costs

The estimation of operating costs is also detailed in Chapter 3.

The annual operating costs for the Mobility Hub scheme are summarised in Table 9.

Table 9. Operating costs

| Hub location | Annual operating costs (£, 2021 prices) |
| --- | --- |
|  | Opening year | Year 2 | Year 3+ |
| St Andrews | 63,000 | 53,000 | 23,000 |

Operating costs have also been converted to market prices, as explained for capital costs. Operating costs are expected to take place every year of the appraisal period, from scheme opening.

## Scheme demand and benefits

### Overview of approach

The overall approach to assessing Mobility Hub demand and benefits is summarised in Figure 7, with the key ‘steps’ in the process described in the remainder of this section. The diagram depicts how the overall benefits are developed based on:

Step 1 – Identifying the in-scope demand i.e. Mobility Hub users who will benefit from the investment

Step 2 – Quantifying the benefits split by type of benefits and to whom they accrue. There are essentially two categories user – ‘existing’ users who benefit from the improved ambience and quality that the Mobility Hub provides, and benefits that result from modal shift.

Step 3 - This takes the demand and benefits for a single year, and monetised and profiles them over the appraisal period in line with appraisal guidance.

Figure 7. Overview of benefits assessment

## Step 1 – base demand for Mobility Hub

The Mobility Hub scheme elements will potentially benefit all users of the Mobility Hub. The base demand is set out in Table 10.

Table 10. Base demand

| Mobility Hub | Base demand (annual trips) | Source / assumptions |
| --- | --- | --- |
| St Andrews Bus Station | 893,000 | Steer estimate |

A secondary assumption has been made about the proportion of demand at the Hub that accesses / egress by each mode. This represents the proportion of trips to the bus station, that are assumed to access by each mode.

These proportions are high level estimates but reflect the specific characteristics of the Mobility Hub location, such as the existing walking and cycling catchments and the level of provision of bus services. The existing access mode share for a group of 12 railway stations in East Fife, as per the data provided by Fife Council, has also been taken into account to produce these estimates.

Table 11. Base demand (mode share assumptions)

|  | St Andrews |
| --- | --- |
| Bus | 15.0% |
| Car (driving) | 35.0% |
| Car (passenger) | 5.0% |
| Taxi | 10.0% |
| Bicycle | 5.0% |
| Walking | 30.0% |
| Total | 100.0% |

## Step 2a – benefits to existing users

### Ambience benefits

Ambience benefits are expected to be perceived by users of the Mobility Hub due to the proposed improvements to public realm, cycle and EV car club parking provision, improved signage and wayfinding, etc. While some improvements will impact all users of the hub, others will be specific to certain users, depending on the access mode (e.g. EV car club parking provision will benefit car club users only).

For the calculation of these benefits, the Ambience Benefit Calculator tool (ABC, v2.24), developed by TfL, has been used. Each proposed improvement measure has been linked with an attribute in the ABC tool, which in turn provided a monetised value of the improvement, in pence per trip.

Table 12. Ambience attribute values

| Attribute | Benefit | Unit | Users impacted |
| --- | --- | --- | --- |
| Seating | 3.80 | pence per trip, 2014 prices | All |
| Parklet, plants and public art | 5.90 | pence per trip, 2014 prices | All |
| Cycle Parking Provision | 20.22 | pence per trip, 2014 prices | Bicycle |
| On street information | 2.64 | pence per trip, 2014 prices | Bicycle |
| Retail units (coffee cart) | 7.30 | pence per trip, 2014 prices | All |
| Local Map | 4.68 | pence per trip, 2014 prices | Bus |
| Finding your way around the station - signage | 2.71 | pence per trip, 2014 prices | All |
| Public Realm access 1 – Street Lighting | 0.80 | pence per trip per minute, 2014 prices | All |
| Public Realm access 2 – Signs to public transport and attraction | 1.60 | pence per trip, 2014 prices | All |
| Public Realm access 3 – Pavement condition | 0.25 | pence per trip, 2014 prices | All |
| Public Realm bus stop 1 – Brightness of lighting | 5.08 | pence per trip, 2014 prices | Bus |
| Public Realm bus stop 2 – Type of shelters | 1.03 | pence per trip, 2014 prices | Bus |
| Public Realm bus stop 3 – Bus stop condition | 0.80 | pence per trip, 2014 prices | Bus |

For those improvements expected to impact all users, the monetised ambience value of the improvement has been applied to the total forecast hub demand.

#### Overall implied benefit per trip (ambience)

      - The overall benefit per trip, taking account of the number of Mobility Hub attributes that benefits each category of user (by access mode), is summarised the tables below. While some improvements will produce ambience benefits for all users, others will only impact those users accessing the hubs on certain modes (e.g. by bus or bike). These are presented for the DS1 and DS2 scenarios.

Table 13. Average benefit per user, Do Something 1 (£, 2014 prices)

|  | St Andrews |
| --- | --- |
| Bus | - |
| Car (driving) | - |
| Car (passenger) | - |
| Taxi | - |
| Bicycle | 0.23 |
| Walking | - |
| All | 0.17 |

Table 14. Average benefit per user, Do Something 2 (£, 2014 prices)

|  | St Andrews |
| --- | --- |
| Bus | - |
| Car (driving) | - |
| Car (passenger) | - |
| Taxi | - |
| Bicycle | 0.23 |
| Walking | - |
| All | 0.17 |

### Public realm benefits

The attributes above relate to Mobility Hub benefits that accrue to users, based on the facilities located at the Hub Location, within the vicinity of the rail or bus station.

The ‘ambience’ benefits do not apply to the benefits of wider public realm measures that form part of the St Andrews Mobility Hub definition and costs, which are part of the DS2 scenario.

We have assumed a benefit per trip of 5 pence per trip (in 2014 prices, consistent with the ABC values listed above) applied to all St Andrews demand to reflect the benefits of wider public realm measures.

## Step 2b – forecasting modal shift

The scheme will have an impact on existing or baseline users of the hub in St Andrews, but it also has the potential to encourage additional users, via modal shift or by generating new trips.

Two elements of the scheme have been identified as potential drivers of mode shift to sustainable modes:

Bike share; and

EV car club.

These elements are likely to generate some level of mode shift from cars to active modes or public transport. This creates a positive benefit, as it reduces the negative externalities that arise from car use, such as congestion, air quality or greenhouse gas emissions.

The bike share systems will also generate health and absenteeism benefits as a result of additional bike users, a proportion of which are likely to shift from car or taxi.

All other elements of the scheme, which involve the improvement of public realm, signage and wayfinding and other measures at the hubs, are assumed to have ambience benefits on existing or baseline users, but no additional demand as a result of these changes has been considered.

It is assumed that there are no variations in potential demand between DS1 and DS2 scenarios based on improvements suggested in DS2 scenario, which are mainly concentrated on public realm improvements.

### Bike share demand

It has been indicated by University St Andrews that they will procure and introduce a bike share scheme with ~115 bikes and ~35 e-bikes in St Andrews linking it to the Eden Campus in Guardbridge and Leuchars Railway Station as part of the funding received by the University through a MaaS Investment Fund Round 2.

A bike share parking bay is proposed for up to 10 vehicles at St Andrews Mobility Hub and for up to 15 vehicles at Leuchars Mobility Hub with an average of five bikes available to users in each site.

There are currently about 21,000 bike share bikes across the UK, of which ~11,700 are in the central London. On average, 2.3 trips are made on each bike per day. However, this average is largely driven by London scheme usage, where approximately 2.6 trips are made per bike per day. In contrast, bikes in Milton Keynes are hired only once in every two days (i.e. 0.5 trips per bike per day). Therefore, the benchmarks of different schemes usage data has informed the estimate of the potential number of trips per day that could be generated for a St Andrews/Leuchars bike share scheme.

Table 15 presents current level of use of bike share schemes in locations such as Milton Keynes, Watford, Bournemouth, Glasgow, City of London and Brighton (popular schemes across the UK).

Table 15. Benchmarking trips per bike per day, 2019 pre-covid data

|  | Milton Keynes | Watford | Bournemouth | Glasgow | London city (Santander Cycles) | Brighton |
| --- | --- | --- | --- | --- | --- | --- |
| Fleet Size | Standard bikes: 300 | Standard bikes: 200 | Standard bikes: 1,000 | Standard bikes: 710 | Standard bikes: 11,600 | Standard bikes: 600 |
|  |  | e-bikes: 25 |  | e-bikes: 63 |  |  |
| Trips per bike per day | 0.5 trips | 0.7 trips | 0.83 trips (April – September 2019) | 1.9-2.7 trips (peak months) | 2.6 trips | 2.1 trips |

While there is limited evidence across the UK schemes on e-bikes usage rate compared to standard bikes, the evidence from other schemes across Europe such as Bicing in Barcelona and Velib scheme in Paris suggests that e-bikes are hired more frequently (30% - 50% more) than standard bikes. Based on that, a conservative assumption of about 1 trip per day for e-bikes in St Andrews and Leuchars has been made, reflecting the relatively small size of St Andrews (which would indicate lower demand per day per bike), and high numbers of students and visitors (suggesting higher demand).

An average trip length is assumed to be 5 miles (8 km) which is based on the distance from St Andrews to Leuchars.

Table 16. Bike share demand assumptions (Leuchars & St Andrews)

|  | Leuchars / St Andrews combined |
| --- | --- |
| No. Bikes (Additional with scheme) | 10 |
| Usage (bike trips per day per bike) | 1 |
| Average trip length (based on Leuchars <> St Andrews distance) | 8.05 km |
| Assumed mode shift from car/taxi (based on CoMoUK Scotland Report 2019/20) | 28% |

### Car club demand

A dedicated EV car club space would be provided, as part of the Mobility Hub proposal, at the hub in St Andrews.

The typical ratio of car club members to spaces/ cars is around 35 based on the CoMoUK Scotland Car Club survey, 2020 and adjusted to reflect less urbanised areas. For each member, an average reduction of 572 annual miles (920 km) per person was reported in the Carplus Annual Survey of Car Clubs, Scotland 2017/18 report. These assumptions have been adopted for the assessment of car club demand for this appraisal.

Table 17. Car club demand assumptions

|  | St Andrews |
| --- | --- |
| Assumed no. car club members | 35 |
| Reduction in car km per year | 920 |

## Step 3a – benefits from modal shift

The benefits from modal shift arise from the following:

Reduction in ‘externalities’ from reduced vehicle kilometres travelled; and

Benefits to new cyclists, in the form of health and absenteeism benefits.

These are set out below.

### Reduction in vehicle kilometres / modal shift

The overall reduction in vehicle kilometres, by element is summarised in the total reduction in distance travelled by car by Mobility Hub element.

For the bike share and bike hire system, the detailed assumptions on bike usage, average trip length and mode shift from car. A car occupancy rate of 1.5 (National Travel Survey, AMAT).

For EV car club, the detailed assumptions of average distance reduction by club member, based on existing evidence.

Table 18 summarises the total reduction in distance travelled by car.

Table 18. Reduction in vehicle kilometres from Mobility Hub investment

|  | St Andrews |
| --- | --- |
| Bike Share | 2,700 |
| Car club | 32,200 |
| Total | 32,500 |

### Externality benefits

The benefits arising from a reduction of distance driven by cars as a result of mode share to sustainable modes have been estimated using the Marginal External Costs (MECs) approach, as defined by TAG guidance.

For EV car club, Local Air quality and GHG MECs have been calculated with the total distance driven before, as distance driven by EV is assumed to produce no exhaust emissions (assuming change is from petrol/diesel car). All other MECs are calculated with the actual reduction in total distance driven.

TAG provides monetised values of the impact of each MEC category for each car kilometre travelled. The categories include congestion, infrastructure cost, accidents, local air quality, noise, greenhouse gases and indirect taxation.

### Health and absenteeism benefits

Health and absenteeism benefits have been estimated using the Active Modes Appraisal Toolkit (AMAT), developed by DfT. The July 2021 version has been used, which is consistent with TAG v1.15, and includes the latest updates to values of time and the updated discount rates for health impacts.

This has been applied to the number of additional cycle users as a result of the Mobility Hub enhancements (i.e. bike share and bike hire). The benefit reflects the benefits from increased physical activity in the form of:

Reduced risk of cardiovascular illness, the reduction in health costs that result from this reduced risk.

Increased productivity, based on evidence that people who exercise more regularly have, on average, two fewer days absent from work compared to those who don’t exercise regularly.

## Economic appraisal

### Appraisal assumptions

An economic appraisal has been developed, based on latest Government guidance (TAG databook v1.15, July 2021) as the reference, the latest version published by DfT. The key appraisal assumptions are:

The year used for price base and discount reference is 2010 as per TAG guidance.

The appraisal period duration has been set to 30 years, with sensitivity testing including shorter and longer appraisal periods of 20 and 60 years, respectively.

All costs and benefits are discounted by 3.5% per annum

The GDP deflator is used for rebasing purposes and the Green Book discount rates for discounting.

The opening year of the scheme has been set to 2023, with benefits and operating costs accrued from that year onward, for the duration of the appraisal period.

Demand growth of 1% per annum has been assumed for 20-years post opening, with no growth thereafter.

Costs converted to market prices with a factor of 1.19, as per TAG guidance.

### Economic appraisal results

The economic appraisal results, summarised for each Mobility Hub, are presented in the tables below for DS1 and DS2, respectively.

Table 19. Economic appraisal results (30 years) – Do Something 1

| £, Present Value | St Andrews |
| --- | --- |
| Scheme Benefits |  |
| Ambience & public realm | 1,845,000 |
| Health and absenteeism | 101,000 |
| Externality benefits (MECs) | 110,000 |
| Total Benefits (PVB) | 2,056,000 |
| Scheme Costs |  |
| Capital costs | 80,000 |
| Operating costs | 307,000 |
| Renewals costs | - |
| Total Costs (PVC) | 387,000 |
| Economic Performance |  |
| Net Present Value (NPV) = benefits – costs | 1,669,000 |
| Benefit Cost ratio (BCR) = benefits / costs | 5.3 |

Table 20. Economic appraisal results (30 years) – Do Something 2

| £, Present Value | St Andrews |
| --- | --- |
| Scheme Benefits |  |
| Ambience & public realm | 2,351,000 |
| Health and absenteeism | 101,000 |
| Externality benefits (MECs) | 110,000 |
| Total Benefits (PVB) | 2,562,000 |
| Scheme Costs |  |
| Capital costs | 199,000 |
| Operating costs | 307,000 |
| Renewals costs | - |
| Total Costs (PVC) | 506,000 |
| Economic Performance |  |
| Net Present Value (NPV) = benefits – costs | 2,056,000 |
| Benefit Cost ratio (BCR) = benefits / costs | 5.1 |

### Interpretation

The appraisal suggests that the economic performance of the Mobily Hub is strong, demonstrating a cost-benefit ratio of between 5.3 (for DS1) and 5.1 for DS2. The performance for both DS1 and DS2 are therefore broadly comparable.

The economic appraisal of St Andrews Mobility is compelling. Overall, the economic appraisal supports the case for investment based on its value for money performance.

### Sensitivity testing

Several economic case sensitivity tests have been undertaken, with the following assumptions:

ST1: Appraisal period of 20 years (compared to the central assumption of 30-years)

ST2: Appraisal period of 60 years (as above)

ST3: Optimism Bias set to 40% (compared to the central assumption of 20%)

ST4: Break-even test (BCR) from capital costs increase – the change in capital costs whereby the BCR would fall to 1 : 1.

ST5: Break-even test (BCR) from ambience benefits reduction- the change in ambience benefits whereby the BCR would fall to 1 : 1.

Table 21 below summarises the results of the sensitivity tests.

Table 21. Sensitivity test results

|  | St Andrews |
| --- | --- |
| Central case – BCR – DS1 | 5.3 |
| ST1 – BCR | 4.8 |
| ST2 – BCR | 6.0 |
| ST3 – BCR | 5.2 |
| ST4 – capital costs increase (%) | 2086% |
| ST5 – ambience benefits decrease (%) | -90% |
| Central case – BCR – DS2 | 5.1 |
| ST1 – BCR | 4.4 |
| ST2 – BCR | 6.0 |
| ST3 – BCR | 4.8 |
| ST4 – capital costs increase (%) | 1033% |
| ST5 – ambience benefits decrease (%) | -87% |

These sensitivities (ST1 to ST4) demonstrate that the case remains robust under a range of sensitivities. The ‘break-even’ tests (ST4 and ST5) reinforce this, whereby costs would need to increase or benefits reduce significantly (to an implausible level) before the BCR of 1 : 1 was reached.

# Financial case

## Overview

      - This chapter discusses the elements of a Financial Case for the proposed Mobility Hub scheme with respect to how the scheme could be funded, and its ongoing affordability.

## Scheme investment costs

      - The estimated capital costs of the proposed Mobility Hub scheme for both DS1 and DS2 scenarios are presented in the tables below.

Table 22. Capital costs incl. optimism bias – Do Something 1

| Capital Cost (£, 2021 prices) | St Andrews |
| --- | --- |
| Base cost | 58,000 |
| Design, management, procurement, installation | 29,000 |
| Contingency @ 20% | 17,400 |
| Total base capital cost | 104,400 |
| Optimism bias @ 21.7% | 22,620 |
| Total | 127,020 |

Table 23. Capital costs incl. optimism bias – Do Something 2 (including DS1)

| Capital Cost – DS1 +DS2 (£, 2021 prices) | St Andrews |
| --- | --- |
| Base cost | 145,000 |
| Design, management, procurement, installation | 72,500 |
| Contingency @ 20% | 43,500 |
| Total base capital cost | 261,000 |
| Optimism bias @ 21.7% | 56,550 |
| Total | 317,550 |

Within the appraisal, the scheme delivery is assumed to be implemented by 2023, with capital costs incurred in the year before the scheme opens, in 2022. Capital costs for each element of the appraisal are listed in Chapter 3.

## Potential funding options

      - There are several potential funding sources that could be explored. These include:

Network Rail funding (for railway station related content);

Transport Scotland grants;

Local Authority grants (Fife Council);

Regional Authority grants (SEStran);

Funding raised by local community groups (e.g. crowdfunding);

Community Shares Scotland;

Scottish National Investment Bank offer help to support Scotland’s transition to net zero;

Grants: Local Enterprise Partnerships, Business Improvement Districts, lottery, charities;

Accessibility Improvement grants;

Environmental improvement grants; and

Heritage improvement grants.

Some of the potential funding options are presented in Table 24.

Table 24. Funding options

| Fund | Description | Notes |
| --- | --- | --- |
| Places for Everyone (Sustrans) | Sustrans Scotland provides advice, support and funding for the creation of infrastructure that makes it easier for people to walk and cycle for everyday journeys. | They do not expect to be able to accept new applications for new projects until 2022. |
| Smarter Choices, Smarter Places (Paths for All) | Smarter Choices, Smarter Places programme supports Scottish local authorities to encourage more journeys by foot, bike and public transport. | Funds, supported by Transport Scotland, are allocated on a population basis to local authorities, to enable projects to be implemented from April 2021. |
| Active Travel repair stations (Sustrans) | Installation of bicycle repair stations and information points. | NHS, colleges, universities and schools can apply for this funding. |
| The eBike Grant Fund | The funding is available to assist local authorities, public sector agencies, further and higher education institutions, active travel hubs and community groups to adopt ebikes as a sustainable alternative to car journeys. The fund can be used to cover the cost of e-bikes, e-trikes, e-cargo bikes, cargo bikes and trailers, tandems, adapted cycles, and trikes. | The funding can be used to support the bike hire scheme in Leven. |
| Street Design (Sustrans) | Outline designs that the local authority can progress to detailed design and construction with support from the Places for Everyone fund. | The scheme is open to local authorities, constituted community groups, other public agencies and statutory bodies can be the lead applicant. Applications that demonstrate a partnership approach will score more highly. |
| The Cycling Friendly Community fund | Funding of up to £20,000 for bikes or facilities that make cycling more accessible. | Community groups in Scotland who are looking to increase opportunities for people to cycle can apply. |
| Cycling Walking Safer Routes fund (CWSR) | The CWSR fund is a ring-fenced grant from Transport Scotland, with £509,000 allocated for 2021/22. | This funding could be used for some of the public realm works. |
| The Cycle Fund | The Cycle Fund supports the programme set out by the Scottish Government to increase cycling and active travel. It offers organisations the opportunity to work with us to deliver enhanced cycling infrastructure and encourage as many people as possible to integrate cycling into their everyday journeys. | The Cycle Fund will provide up to 50% of project costs. It can be used to support projects which will, for example, upgrade connections between stations and other local services such as schools and town centres. |
| Regional Transport Partnerships support (Sustrans) | To support delivery of active travel infrastructure. | Regional Transport Partnerships can apply. |
| Funding allocated through the Go e- Bike scheme | GO e-Bike is a regional bike share scheme offering electrically assisted bicycles in a range of different contexts. | Funding through the Low Carbon Travel and Transport Challenge Fund (LCTT Challenge Fund) round 2 Currently no additional funding available. The funding (if available) could be used to support the bike hire scheme in Leven. |
| St Andrews Community Trust | The Trust fund projects that fall within the Community Council areas of the Royal Burgh of St Andrews, Leuchars, Strathkinness, Cameron, Guardbridge, Boarhills and Dunino. | Funding for some components of the hubs. |
| National Lottery | Larger amounts of funding (£10,000) could be used to subsidize the scheme for marginalized groups. | BRAG could apply for funding to cover some of the costs of the bike hire scheme in Leven. |
| The Plugged-In Households Grant Fund | £500,000 is available for social housing providers and third sector organisations to allow tenants, local residents and staff access electric vehicles on demand through car share clubs. | Supporting the EV car club as part of a Mobility Hub. |
| Regeneration Capital Grant Fund (RCGF) | The Regeneration Capital Grant Fund, delivered in partnership with COSLA and local government, supports locally developed place-based regeneration projects that involve local communities, helping to tackle inequalities and deliver inclusive growth in deprived, disadvantaged and fragile remote communities across Scotland. | Applications to the fund are invited on an annual basis and, where justified, can potentially cover more than one financial year (subject to available budget). |
| Rural Tourism Infrastructure Fund (RTIF) | The Rural Tourism Infrastructure Fund was established by the Scottish Government and the Fund is managed by VisitScotland on their behalf. To date, £9 million of grant funding has been awarded to 45 projects across rural Scotland, since the start of the Fund in 2018. | RTIF is designed to support collaborative projects that focus on improving the visitor experience in rural parts of Scotland that are facing immediate and damaging pressures on their infrastructure, or negative impacts on communities due to significant increases in visitor numbers |

Funding opportunities evolve over time and may have certain rules and restrictions imposed on them including:

Restrictions on what elements the funding may be used for;

Capping of amounts allocated to professional fees such as project management;

Requirements to have reached a particular design stage before bids can be made; and

Deadlines imposed for when the funding must be expended.

## Affordability

The funding should be allocated to support the ongoing operations of the Mobility Hub.

      - Critically, the economic and strategic case set out in this report demonstrates that the Mobility Hub scheme has the potential to deliver a strong value for money case, which is a fundamental requirement for any scheme (along with deliverability).

### Generating Revenue

While Mobility Hubs are currently an emerging area in the UK and do not have established revenue streams, there are a number of options which can support revenue generation which could include:

Seeking sponsorship for the hub and allow the hubs to be branded accordingly (this may only be effective if all local hubs are branded in the same manner;

Providing adverting space;

Providing vending machines;

Providing space and equipment for temporary retail opportunities such as coffee carts;

Charging for the use of facilities such as secure cycle storage at the hubs.

Over time, service providers within a hub may incur permit fees which can contribute to revenue costs in future when the hubs benefits are assessed and proven

# Management case – delivery plan

## Overview

      - This Management Case presents the different stages of launching and operating a Mobility Hub, and how the new scheme should be planned and delivered, including scoping, procurement, implementation, operations and monitoring and evaluation.

      - Figure 8 presents the key stages required to implement a Mobility Hub:

Figure 8. Mobility Hub implementation stages

## Stage 1 – Planning

      - In the feasibility stage, the goal for the scheme owner/s is to identify the key purpose and objectives of the scheme, for example, encouraging mode shift from private car, improving access to employment/ education, improving health and wellbeing etc.

### Scoping and business case development

      - The next step is to define Mobility Hub’s type, components, and location as well as conducting a business case analysis. This includes a breakdown of estimated costs and potential revenue opportunities, evaluating the financial positioning of the scheme. This analysis also supports application for capital funding. This document covers the scoping and business case development element of Stage 1.

      - Mobility Hubs are best realised when operating as part of an interlinked series of hubs. For optimal impact, Mobility Hubs should be planned as a network integrated with public transport.

### Governance arrangements

      - A Mobility Hub requires a delivery lead who secures the funding and coordinates planning and implementation phases including construction of the hub. In terms of operation, Mobility Hubs could be operated and managed by public or private sectors, outsourced to a management company or managed in a partnership.

      - To maximise the scheme objective (see Chapter 2), it is recommended for either SEStran or Fife Council to become a project sponsor of the scheme representing the leading organisation developing a Mobility Hub.

The responsibilities of a project sponsor could include:

Undertaking funding bids;

Seeking third-party funding;

Setting the budget;

Setting the scope of works/ remit and design brief;

Liaising with stakeholders and users;

Overseeing the procurement and appointment of the design team and main contractor;

Overseeing the design development and construction phases; and

Overseeing the ongoing operation of the hub.

The project sponsor should also make agreements with the key partners and transport and service providers such as bus and rail operators, car club, bike share and bike hire operators, and a company supplying parcel delivery lockers.

The project sponsor should also agree on responsibilities of each stakeholder for operations of the Mobility Hubs area and required components (see operations section below).

### Funding Bid

At this stage, if required, the sponsor should develop and submit a funding bid, with the detailed business case including an implementation plan with the key timelines.

In addition, preliminary marketing and outreach campaigns could be started at this stage in order to gain community interest and support.

## Stage 2 – Initiation

This stage includes detailed planning and design of the scheme and further engagement with key stakeholders.

Procurement (if required)

Depending on the approach taken around procurement of the Mobility Hub, the procurement for a designer can be initiated at this stage which will be led by the project sponsor. The sponsor will prepare the brief for the designer. The project sponsor can appoint the design team either by framework agreement, competitive tender or develop the design in-house.

      - The different options for Mobility Hub procurement are discussed in Chapter 8. An option to secure a combined Design and Build (D&B) contract could be explored at this stage.

### Design development process

      - Detailed design is required to identify the specific location and specification for the hub including the following phases:

Concept design;

Development design; and

Technical design.

Table 25 presents a description of each phase of the design development process.

Table 25. Design development process

| Phase | Description | Role of project sponsor |
| --- | --- | --- |
| Concept design | Preparation of high-level concepts by the design team to provide aspirational level visualisations that may be used for one or more locations | Facilitate the design process and coordinate liaison with stakeholders and users |
| Development design | Preparation of space planning and outline design proposals Commence any necessary planning or regulatory change/ control processes | Facilitate the design process and coordinate liaison with stakeholders and users |
| Technical design | Preparation of detailed design for the purposes of tendering and construction | Facilitate the design process and coordinate liaison with stakeholders and users Facilitate the preparation of the construction procurement either by framework agreement or competitive tender |

CoMoUK has created a set of standards linked to the six factors (choice of sustainable modes, visibility and accessibility, ease of switching between modes, safety, practical facilities and visual, social and community appeal), which need to be considered for a successful Mobility Hub and are the means by which CoMoUK assesses Mobility Hubs when accrediting them.

### Stakeholder engagement

For a Mobility Hub to be planned, constructed, operated and monitored successfully, a wide range of stakeholders must be approached and engaged.

The key objectives of the stakeholder engagement include:

- Ensure that the vision and objectives for each Mobility Hub align with national, regional and local visions and objectives;

- Build consensus and support from local stakeholders for the concept and benefits of Mobility Hubs in each location;

- Collect feedback from transport operators (both public and private), other service providers such as EV charging providers, technology providers and the local community;

- Assess operational and maintenance requirements and procurement routes; and

- Engage local media and all stakeholders, for example inviting them to an official opening ceremony.

Key stakeholders have a significant influence on the project and must be managed closely, which can be undertaken by following a stakeholder engagement plan developed for SEStran and presented in Appendix B. The Stakeholder Engagement plan explores the relevance of each stakeholder type as well as the role or activity performed at different stages of the project.

For this project, a Stakeholder Register was developed with relevant contacts for the planning phase (attached as a separate spreadsheet – shared with SEStran and Fife Council in August 2021).

## Stage 3 – Implementation

At this stage, the project sponsor will be in charge of procurement and construction of the scheme. Decisions about asset ownership and provision of the initial investment should be guided by the lifetime of the asset.

### Procurement

      - The different options for Mobility Hub’s procurement are discussed in Chapter 8. The project sponsor will be expected to procure a contractor to build the hub.

### Construction

Next, construction and installation of the Mobility Hub’s components and facilities should be carried out. This generally takes between three to 12 months depending on the size and nature of work requirements.

### Marketing and outreach

A unified branding plan and marketing strategy for long-term expansion of hubs across the region will be beneficial and desirable. Mobility Hubs require a clear visual identity, with a pillar or sign to ensure visibility and increase customer awareness.

The use of a strong brand and recognised colours and logo will help to raise the profile of Mobility Hubs and provide uniform identity. It is recommended that a marketing strategy covering the whole region is developed including identification of key stakeholders and communication channels. A good marketing strategy will raise awareness, influence public attitudes, encourage and incentivise use and also advise about use (e.g. how to use an e-bike or plug in an EV).

## Stage 4 – Operations

The project sponsor should agree on responsibilities of each stakeholder for operations of the Mobility Hubs area and required components.

There are various Mobility Hub operating models available including the following:

Public sector operated and managed;

Private sector operated and managed;

Outsourced to a management company; and

Community run Mobility Hub.

For the Mobility Hubs in St Andrews, it is proposed for the Fife Council or SEStran to take on responsibility of operating the hub. Fife Council/SEStran could oversee all operations for the hub with the specific components/ services managed by a separate private or public sector bodies (see Table 26).

Whatever the management arrangements, there will be a need to clearly agree responsibilities between the project sponsor/lead and the providers of the different mobility and non-mobility components, through a service level agreement or contractual arrangement. This will include elements such as the time within which a bike share provider or car club provider must replace or repair a faulty vehicle, or the charge point supplier must fix a faulty charge point.

The project sponsor will require appropriate fault reporting mechanisms to these bodies. There will also need to be a clear mechanism for addressing sub-standard performance, for example, a mobility provider failing to repair faulty equipment within a defined timescale.

Table 26. Mobility Hub operations

| Area | Task | Responsible body |
| --- | --- | --- |
| Overall Mobility Hub operations | Cleaning and maintenance of the hub area Gardening contract Digital screen checks and maintenance Monitoring and evaluation Marketing and promotion of the hub | Project sponsor/lead (SEStran or Fife Council) |
| Bike share service in St Andrews and Leuchars | Operations and maintenance of bike share Marketing and promotion Training | St Andrews University will procure the service and sign a Service Level Agreement and contract with the operator. The operator will be responsible for operations of the bike share. |
| EV charging infrastructure in St Andrews | Operations and maintenance | A service provider will operate and maintain the service |
| Car club in St Andrews | Operations and maintenance of car club vehicles Marketing and promotion | St Andrews University will procure the service and sign a Service Level Agreement and contract with the operator. The operator will be responsible for operations of the car club. |

It is recommended for the project sponsor (Fife Council or SEStran) to explore key partnership opportunities with Stagecoach, which operate the bus station respectively. There is an opportunity to incorporate all or some aspects of management of a Mobility Hub within the existing management arrangements (see Table 27).

When a local authority takes on the role of the Mobility Hub operator, it could utilise in-house services - operation and maintenance may be included in existing local authority budgets, such as contracts for street cleaning, lighting and gardening maintenance. The resources with the right skills and knowledge should be allocated appropriately. For example, the Municipality of Bremen, Germany, advises that managing of planning for a network of Mobility Hubs implementation takes approximately 20% of one officer’s time.

Table 27. Potential operational agreements

| Operational task | Comments |
| --- | --- |
| Cleaning and maintenance of the hub | The cleaning and maintenance could be agreed with Stagecoach operating St Andrews Bus Station or existing cleaning contracts with Fife Council |
| Updates and maintenance of EV charging infrastructure | Undertaken under contract the EV charging infrastructure provider. |
| Updates and maintenance of a digital pillar | The screens could be maintained by the same company which services the existing digital screens at the bus stops in Fife |
| CCTV monitoring | Could be added to the existing CCTV operations contract |
| Planting/gardening | The gardening costs could be agreed with Stagecoach operating St Andrews Bus Station or existing gardening contracts with Fife Council. |

## Monitoring and evaluation

### Introduction

Mobility Hubs have the potential to result in positive impacts contributing towards meeting a range of local social, economic and environmental policy goals. Once the hub has been procured and launched, the project sponsor will also need to monitor it and evaluate the performance according to the defined service levels.

The monitoring and evaluation framework proposed below can be used as tool to assess the impacts of Mobility Hubs. It can be tailored to specific objectives and different policy areas. The core metrics are presented in Table 29.

The full breath of impacts which could be measured includes how Mobility Hubs can:

- Promote a reduction in vehicle miles travelled, a shift to sustainable modes and the subsequent environmental benefits;

- Promote walking and cycling and the subsequent health and well-being benefits;

- Lead to easier transition between transport options, resulting in improved connectivity to employment, education, and services;

- Address barriers faced by mobility impaired groups (including the disabled);

- Contribute to sense of community cohesion among residents; and

- Support businesses within and adjacent to provided services.

Table 28 presents a summary of the proposed approach for monitoring and evaluation of the Mobility Hub.

Table 28. Monitoring and evaluation approach

| Data collection from operators/providers | Frequency |
| --- | --- |
| Data collection from operator | Annually It can be linked into other surveys, such as CoMoUK car club annual survey and CoMoUK bike share annual survey. |
| Travel surveys | Annually for at least two first years after implementation |
| Stakeholder surveys | Annually for at least two first years after implementation |

### Metrics

Table 1 below provides an overview of how impacts can be measured in relation to each policy goal.

Table 29: How impacts can be measured

| Policy goal | Metrics to measure | Method |
| --- | --- | --- |
| Core |
| Reduced congestion | Car mileage reduction Modal shift from car to more sustainable modes | Transport operator data & travellers’ surveys |
| Reduced local and global emissions | Car miles converted to low emission car club services Uptake of more sustainable modes Improved air quality data | Travellers’ surveys Air quality data |
| Improved health & wellbeing | Increases in walking and cycling Rating on travel survey for increased active travel and improved travelling environment | Transport operator data & travellers’ surveys |
| Improved quality of traveller experience | Rating on travel survey for improved travelling experience – safety /practical facilities/ comfort /visual and social appeal. Qualitative feedback | Traveller survey & stakeholder surveys |
| Inclusive transport systems | Rating on travel survey for accessibility – physical, visual, digital. Qualitative feedback | Traveller survey & stakeholder survey to disability groups |
| Additional |
| Improved street space | Reduced parking demand | Stakeholder surveys |
| Improved connectivity to employment, education, and services. | Trip purpose data Rating on travel survey for connectivity to services Case studies | Transport operator data & travellers’ surveys |
| Community cohesion | Rating on travel survey for community appeal. Qualitative feedback | Traveller survey & stakeholder surveys |
| Economic uplift | Increased utilisation of transport and non-transport services. | Transport operator and service provider data Stakeholder surveys. |

### Data collection

The methodologies for data collection are outlined below:

- Analysis of transport operator data

Relevant public transport, shared mobility operators and other services providers should be provided with a template which should be used collect data to assess impacts through changes in utilisation levels, members trip patterns and demographics of users. It will capture:

- Assessment of changes in patterns of use before and after the introduction of Mobility Hubs.

- Assessment of differences between patterns of use between Mobility Hub and other non-Mobility Hub sites.

The data should be collected prior to implementation for a baseline, then again 12-months post launch.

Table 30: Measuring success of the scheme

| Metric | How to track | Value for the Council |
| --- | --- | --- |
| Bike share |
| Active riders | Trip data on users | Critical to build long-term stable revenue |
| Trips | Trip data on use | Assess impact and revenue |
| Trips per bike per day | All trips/ number of bikes in circulation | Assess efficiency of the system and capacity management |
| Trip length | Data on trip length | Assess use patterns |
| Car club |
| Number of members | Data on registered members | Critical to build long-term stable revenue |
| Active members | Data on active members | Critical to build long-term stable revenue |
| Trips | All trips made by members | Assess impact |
| Trip length | Data on trip length | Assess use patterns |
| Rail |
| Number of annual trips | Trip data on use | Assess impact |
| Bus |
| Number of annual trips | Trip data on use | Assess impact |

- Travel behaviour surveys

Data can also be collected via a survey to be completed by those travelling, or using services co-located at the hub. The survey will ascertain how the presence of the hub has changed users travel behaviour and the subsequent environmental, social and economic impacts. It also poses questions designed to assess the experience of using the hub against key quality standards:

- Choice of sustainable modes;

- Ease of switching modes;

- Visibility and accessibility;

- Safety;

- Practical facilities; and

- Visual social and community appeal.

CoMoUK have created a draft list of questions which can be provided to SEStran and Fife Council. If they are adopted nationwide, this will allow the sector to build up a larger dataset and comparisons to be made.

The survey will need to be distributed through a range of routes with incentives including but not limited to:

- Operators of specific modes through apps or email addresses where they are known;

- Posters advertising the web address of the survey at the hub;

- Council and local community group networks; and

- Face to face interviews with the travellers at a range of times of the day and week (desirable, if budget allows).

There are range of other methods which can be deployed to supplement a survey when assessing satisfaction with the hub and its services. These range from asking for feedback via social media tags, adding “smile / frown” buttons to press at the hub to digital diaries and focus groups (in larger locations, where budget allows).

- Stakeholder surveys

A final tool to complete the assessment of the impact of the Mobility Hub is to survey local stakeholders such as businesses, community & specialist user groups who may not necessarily be uses of the hub transport services. The list can be adapted depending on surroundings of the site. This survey will collect views on the social, community and economic impacts such as improved access facilities for disadvantaged groups, footfall for local businesses, and improved social cohesion. Such surveys would need to be designed to reflect the local context.

A list of key stakeholders is presented in Stakeholder Engagement Register, which was supplied to SEStran and Fife Council separately.

# Commercial case – system procurement

## Overview

The Commercial case presents how the Mobility Hub and associated new services can be procured.

## Procurement

Mobility Hubs can be procured, operated and managed in a variety of different ways. Procuring a Mobility Hub can either be undertaken by the lead body or can have some or all elements outsourced to a third party so that the lead body can have a hands-off approach.

A local authority may provide funding for a bike share service and infrastructure and have a contract with a bike share operator to provide an agreed service. Alternatively, the local authority may not provide any funding and just give permission to schemes to operate from the Mobility Hub, without the need for a contract.

In general, procurement for Mobility Hubs can include both tenders for service providers (e.g. car club or EV charging infrastructure) and design and construction of the hub. The need for tendering for service providers will depend on existing contracts in the area. For example, where a car club is already present in the area, then there may be no need to re-tender this type of service.

Table 31 below presents a summary of procurement activities required for a Mobility Hub.

Table 31. Mobility Hub operations

| Procurement area | Responsible body |
| --- | --- |
| Mobility Hub |
| Design of a Mobility Hub | Project sponsor/lead (SEStran or Fife Council) |
| Construction of a Mobility Hub | Project sponsor/lead (SEStran or Fife Council) |
| Mobility Hubs’ services/components |
| Bike share service in St Andrews and Leuchars | St Andrews University will procure the service and sign a Service Level Agreement and contract with the operator. |
| EV charging infrastructure in St Andrews | Fife Council will procure the infrastructure to be used by the car club operator. |
| Car club in St Andrews | St Andrews University will procure the service and sign a Service Level Agreement and contract with the operator. |

### Mobility Hub design and construction - procurement options

#### Design of a Mobility Hub

The project sponsor can appoint the design team either by framework agreement, competitive tender or develop the design in-house (if Fife Council/SEStran have resources with required skillset).

The design team will vary in size depending on the complexity of the project and the number of different professional disciplines required to undertake the individual design elements and the coordination of the design as a whole. It may be possible to employ a single design company who will offer all the necessary professional disciplines in a “one stop shop” appointment or appoint individual consultancies depending on their expertise. These may include:

Land Surveyors;

Architects;

Structural Engineers;

Civil Engineers;

Mechanical Engineers; and

Electrical Engineers.

#### Construction of a Mobility Hub

The project sponsor can mainly appoint the construction team either by framework agreement or competitive tender.

#### Design & Build contract

There is also an option to procure a contractor for a Design & Build contract, which will mean that a contractor will be responsible for both design and construction of a Mobility Hub.

A summary of the key options is presented in Table 32 below.

Table 32. Construction procurement options

| Procurement option | Benefits | Challenges |
| --- | --- | --- |
| Separate tenders for design and build | An opportunity to use value engineering to influence the design and the overall price Ability to influence the choice of materials Project sponsor’s input – more opportunities to influence the final design | Timeline could be longer for the delivery, as two separate tenders needs to be procured |
| Design & Build contract | One stage procurement All the risks are with the appointed contractor | The overall price could be higher due to the contingency added by a contractor in the response to the tender Price can be difficult for the bidders to evaluate due to a lack of design information in the specification The contractor may not understand all the risks fully No one bids for the tender as it is considered too risky by the market |

#### Examples of design and construction of Mobility Hubs

To date in the UK there are limited examples of Mobility Hubs which have been designed and built.

Transport for West Midlands (TfWM) appointed the design and engineering firm CALLUM to provide design and engineering services to develop the concept of a modular Mobility Hub, which is currently being tested. This is an example of a Design & Build contract.

The Mobility Hub concept was fully designed, engineered and built by CALLUM for TfWM. Their first Mobility Hub concept was unveiled at the University of Warwick campus during the Micromobility UK event in Summer 2021 (see Figure 9).

Figure 9. TfWM Mobility Hubs concept by CALLUM

Source: CALLUM

In London, Meristem design developed the design of a Mobility Hub for London Borough of Redbridge including a parklet containing planters, seating, cycle parking, Wi-Fi and a water fountain (see Figure 10).

Figure 10. Wanstead Mobility Hub concept by Meristem Design

Source: https://engagement.redbridge.gov.uk/civic-pride/wansteadmobilityhub/user_uploads/wanstead-parklet-design-guide.pdf

### Procurement process

When assessing the best procurement approach the following criteria should be considered by a project sponsor:

Deliverability of the services and practicality of the solutions;

Long term sustainability and operations;

Technical requirements;

Customer experience;

Commercial including potential capital and operational costs and any revenue generation opportunities; and

Managing risk but allowing for innovation.

Early market engagement could be undertaken to:

Confirm market appetite to engage and deliver the scheme;

Confirm procurement assumptions made and gather market intelligence on industry trends and market appetite; and

Understand the level of innovation in the market and it is ability to deliver sustainable solutions long-terms (linked to futureproofing).

### Procurement specification

The level of detail provided in specifications is key to success, the balance between providing a good technical specification as part of the procurement documents and limiting creativity needs to be considered, so that it does not prevent the spirit of innovation and collaboration. Steer generally promotes the use of outcome-based specifications with a user-centred approach.

It is recommended for a procurement specification to include the following:

Objectives and definition of local requirements for each lot and strategic fit with the Council’s overarching objectives.

Confirmation of required services and facilities; and

Required design and technical specifications.

It will be important to develop a specification which is a balance between meeting the objectives of the scheme and one which is sufficiently attractive to promote competition in the market. A procurement which is too constrained, or unattractive commercially may result in few or no bidders.

# Conclusion

## Overview

Mobility Hubs will be an important tool to support Fife Council as it seeks to meet the aims and objectives outlined in the National Transport Strategy 2 (NTS2), reflected in SEStran’s emerging Regional Transport Strategy (RTS) and in the development of a new Local Transport Strategy (LTS) for Fife. These include reducing inequalities; taking climate action; helping deliver inclusive economic growth; and improving health and wellbeing.

This document presented the technical assessment and business case for a Mobility Hub in St Andrews which could form the basis for a funding submission. This document also examined the costs associated with funding the capital, operating and renewal costs.

## St Andrews Mobility Hub

In addition to providing a range options for residents, a Mobility Hub in St Andrews can support the current visitor and tourism offer for the University and golfing town, helping to increase the active travel options available, reducing the pressure that high traffic volumes put on the town’s medieval infrastructure and environment.

It is proposed that a Mobility Hub is located with services both at St Andrews bus station and within the car park adjacent to the bus station. This location was selected as the bus station is the focus for public transport in the town and is situated in a central location serving both the town centre and University.

The bus network is crucial in linking St Andrews to the railway network approximately 6km away in Leuchars, and to airports which are further afield. St Andrews is linked by a cycle path from the centre of St Andrews to within 500m of Leuchars railway station.

Based on the analysis, stakeholder engagement and site visits, it is recommended that the hub would be comprised of the elements presented in Table 33.

Table 33. St Andrews Mobility Hub

| Existing facilities | Do Something 1 (DS1) | Do Something 2 (DS2) |
| --- | --- | --- |
| Bus station: Secured cycle storage (the bus station has six unsheltered Sheffield hoops and six secure cycle storage lockers) Taxi rank/pick up drop off area Wi-fi Digital pillar with bus information Shop within the station Toilets Left Luggage Waiting room CCTV Cameras | Bike repair stand/bike pump Two EV car club parking bays with a single EV charging station with two charge points Bike share parking bay (for up to 10 vehicles) Parklet/seating facilities Updated digital information pillar Additional signage and wayfinding on the platforms, at the bus stop, at the hub area including tourist information Additional CCTV provision (at the car park) | Public realm improvements (access to car park and link to the city centre) Phone charging facilities |

Figure 11. Potential location for the Hub’s key facilities

We have reviewed a range of national, regional, and local policy and strategy documents which demonstrated support for Mobility Hubs and improvement of connectivity and sustainable transport options. To ensure the review remains focussed on the proposed Mobility Hubs in East Fife specifically, the policy review is structured around six key objectives developed in the SEStran Mobility Hubs Feasibility study and adapted for this study:

- Embracing innovation - Mobility Hubs can bring together traditional and innovative mobility and non-mobility services in a visible and easily recognisable places that increase awareness of alternative travel choices and useful services and encourage higher usage by residents and visitors alike.

- Improving accessibility/ equity and inclusion - App based services disproportionately benefit smart phone users. The physical availability of real time travel or tourism information, ticketing facilities and other non-mobility services can further help bridge the gap in access to services between technology users and non-users

- Reducing emissions - Mobility Hubs have the potential to positively contribute to climate and air pollution targets by reducing the number of vehicles/cars on roads, lowering use and car ownership rates among users, and supporting the shift of trips to environmentally friendly modes of transport such as cycling.

- Improving health and wellbeing - Availability of secured cycle parking alongside servicing tools and equipment at the Mobility Hubs can encourage more people to cycle their first and last mile of the journey as compared to using private cars (which are generally parked at monitored/secured car parks) promoting health and wellbeing.

- Promoting a stronger economy - In addition, there are wider benefits in terms of increased productivity and quality of life owning to reduced congestion, improved air quality, higher use of shared and active transport and public realm improvements which positively support the case for Mobility Hubs in promoting a stronger economic growth.

- Resilience from the Covid-19 pandemic - Mobility Hubs supporting shared micromobility schemes can lead to a positive behavioural change towards use of micromobility supporting long term sustainability goals.

St Andrews is a university town where St Andrews University has around 10,000 students and is also the main employer in the area. St Andrews is also popular tourist destination with more than 675,000 tourists visiting the town per a year pre the Covid-19 pandemic. The total population of St Andrews is 17,580 (2016 est.).

Driving is the most common mode of transport for commuting in St Andrews Central at 49%, with areas outside of the main centre having a higher car mode share. Walking is the second most popular mode of commute with a share of 32% with majority of the residents in the north and east of the town centre walking to work.

The proposed Mobility Hub at the St Andrews Bus station is planned to improve transport connections and provide alternative modes of travel for residents, visitors and the student population.

About 15,000 St Andrews residents live within five minutes cycling distance from the proposed location and almost the entire population is located within 20-min cycling distance to the St Andrews bus station. This means that providing bike share options at the bus station would allow for car trips to be replaced by a combination of cycling and public transport.

The St Andrews Bike Share Feasibility Study 2019 undertaken by the University highlights that ‘many residents state they would replace their current personal car use with a public bike share if one were available and convenient for them, this would ease congestion in the centre of town and open up parking spaces. Long term access to the centre of the town without a car could reduce the need for cars in the centre of town entirely’.

Through user research, the study also found that people who are employed in St Andrews but are not residents (approx. 12,000 persons) would like to have a bike share location in transport interchanges such as the St Andrews Bus Station to be able to use the scheme. This clearly demonstrates the potential demand that exists in the area for a Mobility Hub, which can potentially reduce car dependence by improving first and last mile connectivity if it’s provided to serve key destinations and origins across the urban area and with services available for an attractive fee. The University are in the process of procuring a bike share scheme.

According to the Strategic Transport and Travel Plan 2020-2025 for the University of St Andrews, it plans to secure growth the number of students by 2025, which will require provision of smart and sustainable travel choices that will help meet the University’s commitment to sustainability including reduction of emissions associated with transport.

The proposed Mobility Hub (which is within 5-10 mins walking distance to the University campuses) could potentially positively help address its existing and increasing travel needs by staff, students, visitors and travel needs associated with business activity and services.  As identified in the STTP, central to this will be extending travel choices, developing services, and promoting changes that will offer improved accessibility, and deliver environment, place and community benefits.

While there are already some shared mobility choices available at the University such as Go e-Bike scheme, as well as a staff car sharing scheme, a visible and well promoted Mobility Hub with a dedicated space bringing all the services together will help increase the awareness of the services, and encourage more people, including staff, students and visitors, to replace car trips with shared transport options.

E-Car club was present in St Andrews until October 2019 with operations overseen by St Andrews University. The club consisted of ten electric vehicles which served the university’s staff and students but were not easily available for the residents and visitors to St Andrews with all cars located on University land. Analysis of Scotland’s car club market, funded by Carplus through the Developing Car Clubs in Scotland (DCCS) programme in 2011, identified St Andrews as one of the top five small urban areas in Scotland in which to develop a car club. University of St Andrews MaaSterplan was awarded MaaS Fund Round 2 funding in 2021, for a pilot to promote community-centred mobility services that will tackle issues such as congestion and achieving the transition to net zero, promoting sustainable, active and shared transport options. An EV Car Club is part of the proposals and it is expected that the University will procure a car club operator.

The appraisal suggests that the economic performance of the Mobily Hub is strong, demonstrating a cost-benefit ratio of between 5.3 (for DS1) and 5.1 for DS2. The performance for both DS1 and DS2 are therefore broadly comparable.

The economic appraisal of St Andrews Mobility is compelling. Overall, the economic appraisal supports the case for investment based on its value for money performance.

Appendix A. Leuchars and St Andrews: technical assessment

Introduction

      - The Appendix presents the results of technical assessment for a feasibility study to establish how Mobility Hubs could be delivered in conjunction with key proposed rail (and bus) interchanges at Leuchars and St Andrews.

Study Area

      - Leuchars is a relatively small town with a population of around 2,340 (2016 est.), located near the north-eastern coast of Fife. It is located approximately six miles from the University town of St Andrews. Within Leuchars, this study will focus on the area surrounding Leuchars Railway Station.

      - St Andrews is located to the south-east of Leuchars, approximately 10 miles south-east of Dundee and approximately 30 miles north-east of Edinburgh.  With a population of 17,580 (2016 est.), it is Scotland’s 45th most populous settlement. The town is known as the “home of golf” mainly due to The Royal and Ancient Club of St Andrews situated in the north-west of the town. The town is also famous for its university which has approximately 10,000 students (2020). Within St Andrews, this study will focus on the area surrounding St Andrews Bus Station.

### Transport Provision

      - Leuchars Railway Station is located to the south-west of Leuchars, with regular services between Edinburgh, Fife, Dundee and Aberdeen. The railway station has 325 parking spaces, an electric charging station, sheltered cycle parking for 10 bicycles, a taxi rank and bus stop.

      - Figure 12 below shows the key trip attractors within the Leuchars and St Andrews Area.

Figure 12. Leuchars and St Andrews area trip generators

### Key Employers

      - St Andrews’ economy relies heavily on tourism and education. The University of St Andrews is one of the key employers in St Andrews, having approx. 1,200 academic staff and approx. 1,600 admin staff. Around 400 people are employed by St Andrews Links Trust in the peak season making it one of the largest employers in St Andrews.

      - Leuchars Station is British Army installation based in Leuchars.  There are around 100 civil servants and 750 UK Regular Forces, supported by around 30 Full Time Reserve Service personnel, based at Leuchars.

      - Other key employers include Madras College, St Leonards School, a wide range of supermarkets, as well as local bars and restaurants.

### Demographics

      - As shown in Figure 13 below, the majority of areas in St Andrews and Leuchars are among the least deprived in Scotland. There are some areas such as the north-west of Leuchars and southern areas of St Andrews which are within the 4th and 5th most deprived areas in Scotland, according to the Scottish Index of Multiple Deprivation (SIMD).

Figure 13. Deprivation levels in the Leuchars Area

Multi-modal transport analysis

      - This section analyses the existing and proposed multi-modal transport network within Leuchars, St Andrews and beyond. This includes walking and cycling, bus, train and private vehicles. Datashine Scotland census data is also presented to show how people in the area travel to work.  This analysis will allow for informed decisions about the location and nature of potential Mobility Hubs in the Leuchars and St Andrews.

### Walking and Cycling

      - Figure 14 below shows the existing active travel network for the area surrounding Leuchars Railway Station. National Cycle Route 1 connects Leuchars to St Andrews to the south-east. This route is mainly off-road, with some on-road sections. The route between the two settlements is approx. 5.5 miles, or an approx. 30-minute cycle. There is a footway along Station Road, connecting the centre of Leuchars, to Leuchars station.

      - Figure 15 shows the existing active travel network in and around St Andrews, including locations of “Go E-Bike” hangars. “Go E-Bike” is a shared electric bike scheme run by the University of St Andrews with aims to reduce private car use by providing an alternative travel mode for staff moving to the new the Eden Campus which is 4 miles from the centre of town; create a new transport link between the town and Leuchars train station for staff; provide staff with a fast and efficient method of moving around town without vehicle; and to promote Cycling and E-Bikes as a way of commuting to work. BikePool is a community group in St Andrews which refurbishes old bikes and rents them to students and locals for an affordable price. They also run “Fix It” sessions to keep your bike in shape.

      - In July 2021, a Bike Share feasibility study was undertaken by Transition University of St Andrews which concluded that if stations are placed intelligently to serve tourist needs, even a small percentage of tourists utilising the scheme could provide enough income to subsidize the scheme for everyone who calls St Andrews their home. The study recommends bike hire stations at Leuchars Railway Station and St Andrews Bus Station, among other locations.

      - Figure 16 shows an annotated Sustrans’ map of cycling facilities in and around St Andrews, including cycle parking; cycle shops/maintenance; recommended routes; electric vehicle locations; electric vehicle charge points; and public toilets.

Figure 14. Leuchars Active Travel Network

Figure 15. St Andrews Active Travel Network

Figure 16. St Andrews existing cycling facilities

#### Walking Journey Times to Leuchars Railway Station

      - Figure 17 below shows the walking times to Leuchars Railway Station, for 5, 10, 15 and 20-minute durations. There are no residents within a five-minute walk of the site.  However, there are approx. 200 within a 10-minute walk, approx. 800 within a 15-minute walk and approx. 2,400 within a 20-minute walk. This shows that for large proportions of the residents of Leuchars, it is over a 15-minute walk to the railway station. Although a 20-minute walk is still viable, alternative modes such as cycling or public transport may be more attractive.

Figure 17. Walking Journey Times to Proposed Leven Rail Station

#### Cycling Journey Times to Leuchars Station

      - Figure 18 below shows the cycling times to Leuchars Railway Station for 5, 10, 15 and 20-minute durations. There are approx. 3,200 people within a five-minute cycle of the site, approx. 5,100 within a 10-minute cycle, approx. 6,100 within a 15-minute cycle and approx. 9,300 within a 20-minute cycle. The majority of the population of Leuchars lives within a 5-10-minute cycle of the station. For the majority of residents of St Andrews, Leuchars station is greater than a 20-minute cycle, meaning public transport may be preferred. E-bikes would also be an attractive option for an approx. 30-minute cycle.

Figure 18. Cycling Journey Times to Leuchars Railway Station

#### Walking Journey Times to St Andrews Bus Station

      - Figure 19 below shows the walking times to St Andrews Bus Station, for 5, 10, 15 and 20-minute durations. There are approx. 2,100 people living within a five-minute walk of the site, approx. 6,700 within a 10-minute walk, approx. 9,000 within a 15-minute walk and over 11,400 within a 20-minute walk. This shows that the majority of the population of St Andrews lives within a reasonable walking distance of the Bus Station. Those living out-with a 20-minute walk may favour cycling or public transport for accessing the bus station, for onward travel.

Figure 19. Walking Journey Times to St Andrews Bus Station

#### Cycling Journey Times to St Andrews Bus Station

      - Figure 20 below shows the cycling times to St Andrews Bus Station, for 5, 10, 15 and 20-minute durations. There are currently only approx. 15,000 people within a five-minute cycle. This represents the majority of people living in St Andrews. There are also approx. 17,500 within a 10-minute cycle, approx. 18,400 within a 15-minute cycle and approx. 19,400 living within a 20 minute cycle of the bus station. There may however be bus stops en route that may be closer for some of these residents.  With the majority of the population residing within a realistic cycling distance of the bus station, proving adequate facilities at the bus station would allow for more long-distance trips to be made by a combination of cycling and public transport.

Figure 20. Cycling Times to St Andrews Bus Station

### Public transport

#### Leuchars

      - The main train station serving the Leuchars and St Andrews areas is Leuchars Railway Station, located just to the south of Leuchars. The weekday services calling at Leuchars are as follow:

- London North Eastern Railway:

- 3 trains per day (tpd) to London King's Cross. These trains are from Aberdeen;

- 1 tpd to Leeds from Aberdeen;

- 4 tpd to Aberdeen. Three of these trains are from London King's Cross and the other, an early-morning service, is from Leeds.

- Cross Country:

- At the 12th May 2021 timetable change, CrossCountry do not serve Leuchars.

- Caledonian Sleeper:

- 1 tpd to London Euston via Edinburgh, Preston and Crewe;

- 1 tpd to Aberdeen.

- Scotrail:

- 2 tph to Edinburgh;

- 1 tph to Aberdeen;

- 1 tph to Arbroath.

      - Leuchars Railway Station is served by Stagecoach services 99A, 99B, 99C and 99D which connect St Andrews, Leuchars and Dundee. It is also served by Stagecoach service 42A to Dundee, 92A to Tayport and 94A to Newburgh. Services between Leuchars and St Andrews are frequent, approx. every 5-10 minutes during the day.

### Public Transport Journey Times to Proposed Leuchars Station

      - Figure 21 below shows the public transport journey times to Leuchars Station, for 0-5-, 5-10-, 10-15- and 20–30-minute durations.  The journey times have been produced using the TRACC software, which is the market leader in public transport analysis. The data shows that for Leuchars Station, the majority of the largest settlements in north-east Fife, such as Leuchars, St Andrews, Cupar, Newport, Tayport, Wormit and Gauldry can access via public transport within 30 minutes.

      - Areas around the centre of St Andrews are within a 10–15-minute public transport journey of Leuchars Station. Those living in outer areas of the settlements may have to walk for approximately 5-15 minutes to access bus services to the station, but this is not considered unreasonable in terms of overall journey time, making multi modal (walking/bus) trips reasonably attractive for large proportions of the population within the station’s catchment area.

Figure 21. Leuchars Station Public transport time in minutes

St Andrews

      - The bus station in St Andrews is located on Station Road, just to the west of the centre of the town. The Stagecoach bus route map is shown in Figure 22. The full list of services available at St Andrew are shown in Table 34 below. Many of the below services call at Leuchars Railway Station, allowing for a frequent service between the town and the railway station. Services run at a frequency of approx. 8 minutes and the journey takes approx. 15 minutes.

Figure 22. St Andrews Bus Route Map (Stagecoach)

Table 34. St Andrews Bus Station Routes

| Service No. | Destination |
| --- | --- |
| 42A | Dundee City Centre |
| 59 | Edinburgh |
| 94 | Leven |
| 94A | Newburgh |
| 94X | Newburgh |
| 95 | Leven |
| 97 | Largoward |
| 99 | Dundee City Centre |
| 99A | Dundee City Centre |
| 99B | Dundee City Centre |
| 99C | Dundee City Centre |
| 99D | Dundee City Centre |
| CG1 | Canongate Primary School |
| X24 | Glasgow |
| X59 | Edinburgh |
| X59A | Edinburgh |
| X60 | Edinburgh |

### Public Transport Journey Times to Proposed Leuchars Station

      - Figure 23 below shows the public transport journey times to St Andrews Bus Station, for 0-5-, 5-10-, 10-15- and 20–30-minute durations.  The journey times have been produced using the TRACC software, which is the market leader in public transport analysis. The data shows that for St Andrews Bus Station, the majority of the largest settlements in north-east Fife, such as Leuchars, Cupar, Newport, Tayport, Wormit, Gauldry, Crail and Anstruther can access via public transport within 30 minutes.

      - Other settlements such as Lundin Links are just outside 30 minutes access time but are served by buses. The whole settlement of St Andrews is within a 10–15-minute bus journey of the bus station, making the bus an attractive mode of transport into the center of town. St Andrews is also well served by buses to and from Dundee, just beyond a 30-minute bus journey. Day trips from Dundee to St Andrews are popular, particularly in summer months. People making the journey from Dundee by bus could benefit from bikes being available to hire from near the bus station, to access locations around the St Andrews area, which may be beyond reasonable walking distance.

Figure 23. St Andrews Bus Station Public transport time in minutes

### Road Network

      - The A91 Is the main east-west distributor road that serves the area, connecting St Andrews to Leuchars, Cupar and onwards to the west. The A915 is the main road to the south of St Andrews, connecting it to areas in East Fife, including Levenmouth and Kirkcaldy.

### Parking

      - Leuchars Railway Station has a car park with 325 spaces, including six electric vehicle charging space and 15 disabled spaces.

      - At St Andrews Bus Station, there is no designated car parking available. However, free parking is available in Petheram Bridge Car Park, with space for 318 cars. The car park is 150 metres from the Bus Station via a 3° inclined path or Station Road (5° incline). Car access is from North Haugh or Doubledykes Road.

### Shared mobility

#### E-Car Club

      - The E-Car club was present in St Andrews until October 2019. Work is underway to find a replacement service for the community. Analysis of Scotland’s car club market, funded by Carplus through the Developing Car Clubs in Scotland (DCCS) programme in 2011, identified St Andrews as one of the top five small urban areas in Scotland in which to develop a car club.  The club consisted of 10 electric vehicles.

      - University of St Andrews MaaSterplan was awarded MaaS Fund Round 2 funding, for a pilot to promote community-centred mobility services that will tackle issues such as congestion and achieving the transition to net zero, promoting sustainable, active and shared transport options. An E-Car Club was part of the proposals.

#### University of St Andrews Lift Share Scheme

      - The University's lift share scheme allows people to enter their destination and be matched with other people going the same way. This reduces the number of cars on the road and helps people save money.

#### G E-Bike

      - “Go E-Bike” is a shared electric bike scheme run by the University of St Andrews with aims to reduce private car use by providing an alternative travel mode for staff moving to the new the Eden Campus which is 4 miles from the centre of town; create a new transport link between the town and Leuchars train station for staff; provide staff with a fast and efficient method of moving around town without vehicle; and to promote Cycling and e-Bikes as a way of commuting to work.

#### E-bike share

      - In July 2021, a Bike Share feasibility study was undertaken by Transition University of St Andrews which concluded that If stations are placed intelligently to serve tourist needs, even a small percentage of tourists utilizing the scheme could provide enough income to subsidize the scheme for everyone who calls St Andrews their home. The study recommends bike hire stations at Leuchars Railway Station and St Andrews Bus Station, among a total of 18 locations.

### Datashine Commute Data

      - DataShine Scotland utilises the DataShine framework to map selected Quick Statistics and Key Statistics for Scotland’s 2011 Census. Table 35 below shows the number of commuting trips by mode from various areas of St Andrews and Leuchars. Table 36 shows the mode share for each area.

      - The data shows that there is a relatively high percentage of car commute trips, with St Andrews South West and St Andrews North and Strathkinness having the highest percentage (68% and 63% respectively).

      - Central St Andrews has the lowest percentage of commuting trips via driving, with a relatively higher percentage of commuting by bus and by foot in this area. The highest percentage of walking commuting trips are in St Andrews South East. The highest percentage of cycling commuting trips are in Leuchars and Guardbridge.

Table 35. Datashine Commute Totals by Mode

|  | St Andrews Central | St Andrews South East | St Andrews South West | St Andrews North and Strathkinness | Leuchars and Guardbridge |
| --- | --- | --- | --- | --- | --- |
| Train | - | - | - | - | - |
| Bus | 434 | 62 | 59 | 135 | 160 |
| Car (driving) | 1,967 | 815 | 1,139 | 1,571 | 743 |
| Car (passenger) | 205 | 76 | 54 | 87 | 76 |
| Bicycle | 119 | 54 | 72 | 115 | 150 |
| On foot | 1,295 | 540 | 355 | 585 | 319 |

Table 36. Datashine Commute Percentages by Mode

|  | St Andrews Central | St Andrews South East | St Andrews South West | St Andrews North and Strathkinness | Leuchars and Guardbridge | Overall |
| --- | --- | --- | --- | --- | --- | --- |
| Train | 0% | 0% | 0% | 0% | 0% | 0% |
| Bus | 11% | 4% | 4% | 5% | 11% | 11% |
| Car (driving) | 49% | 53% | 68% | 63% | 51% | 49% |
| Car (passenger) | 5% | 5% | 3% | 3% | 5% | 5% |
| Bicycle | 3% | 3% | 4% | 5% | 10% | 3% |
| On foot | 32% | 35% | 21% | 23% | 22% | 32% |

      - Figure 24 below shows the percentage of people travelling to work by foot (Datashine). Those living closer to the town centres in both St Andrews and Leuchars are more likely to walk to work than those outside of the centre.

Figure 24. Commute by Walking (Datashine)

      - Figure 25 below shows the percentage of people travelling to work by Bicyle (Datashine). The highest cycle mode share is in the area to the west of the centre of St Andrews. As shown in Table 35 actual cycle trip numbers are generally high throughout the Leuchars and St Andrews area. Providing adequate infrastructure at Leuchars Station would allow for those commuting by train to make part of their journey by bike. This combination of modes may be able to replace some car commute trips.

Figure 25. Commute by Cycling (Datashine)

      - Figure 26 below shows the percentage of people travelling to work by bus, minibus or coach (Datashine). There is generally quite a low mode share for bus throughout the St Andrews and Leuchars area.

Figure 26. Commute by Bus (Datashine)

      - Figure 27 below shows the percentage of people travelling to work by train (Datashine). There is generally quite a low mode share for train throughout the St Andrews and Leuchars area. Highest percentages are in the immediate area surrounding Leuchars Station, as well as a number of smaller locations, mostly on the peripheral of St Andrews.

Figure 27. Commute by Train (Datashine)

      - Figure 28 below shows the percentage of people travelling to work by car (Datashine). Driving is the most popular mode of transport for commuting, with areas outside of the main centres having the highest percentage.

Figure 28. Commute by Car (Datashine)

      - Figure 29 shows the destination of car commuting trips from St Andrews (Datashine). Popular locations include Leuchars, Crail, Ansthruther, Pittenweem, Ceres, Cupar, Balullo, Newport-on-Tay and Tayport. Most, if not all, of the destinations listed above are served by bus from St Andrews, meaning there is potential for a number of car commute trips to be converted to bus.

Figure 29. Car Commuting Trips to (blue) and From (red) St Andrews (Datashine)

      - Figure 30 shows the destination of car commuting trips from Leuchars (Datashine). Popular locations include St Andrews, Tayport, Balullo and Cupar. There is potential for a number of trips, particularly to Cupar, to be made by train.

Figure 30. Car Commuting Trips to (blue) and From (red) Leuchars (Datashine)

#### University of St Andrews Travel Survey

      - A survey of University of St Andrews staff undertaken by Stantec in 2019 found that:

- 68% of staff drive to work (60% in 2015), with 46% driving alone;

- 8% use the bus (12% in 2015);

- 7% cycle (9% in 2015);

- 12% walk (15% in 2015);

- 3% travel by train (3% in 2015).

      - The data shows the walking and cycling mode shares, along with bus use, declined between 2015 and 2019. The top interventions staff wanted to see in order for them to consider cycling were:

- Improved/more cycle paths on journey to work;

- Improved changing facilities/showers/lockers at work;

- Maintenance assistance e.g. Bike Pool;

- Improved/more secure, covered cycle racks;

- 25% of respondents reported that they would use an electric bike rental service at least once a month.

Landownership and Planning

      - This section provides an overview of the current land ownership information and well as relevant planning information.

### Land Ownership

      - Figure 31 below shows the landownership information for the proposed Leven Rail Station site.

Figure 31. Leuchars Station Land Ownership Information (the areas coloured in pink are owned by Fife Council)

      - Figure 32 below shows the landownership information for the proposed Cameron Bridge Rail Station site.

Figure 32. St Andrews Bus Station and University Land Ownership Information (the areas coloured in pink are owned by Fife Council)

### Planning

      - Figure 33 below shows Fife Council’s Local Development Plan Proposals and Development Requirements.

Figure 33. St Andrews Local Development Plan Proposals

      - Table 37 below shows details of the proposed developments. The estimated capacity for housing gives an indication of the level of growth expected in the near future.

Table 37. St Andrews Local Development Plan Proposals

| Ref | Location | Area (ha) | Description | Est Capacity (housing) | Lead Agency |
| --- | --- | --- | --- | --- | --- |
| STA 001 | St Andrews West | 113.4 | 1,090 houses, to be developed on a phased basis in distinct neighbourhoods or “hubs”. | 1090 | University of St Andrews/ Private Sector/Fife Council |
| STA 002 | Grange Road | 2.2 | University related housing development | 50 | University of St Andrews |
| STA 003 | New Park School | 1.5 | Housing development | 21 | Private Sector |
| STA 006 | St Leonards | 4.4 | Housing/Hotel | 240 | Private Sector |
| STA 007 | St Leonards Lodge | 0.2 | Employment | - | Private Sector |
| STA 008 | Strathyrum | 7.1 | Employment/Hotel | - | Private Sector |
| STA 009 | Flemming Place, Kinnessburn and Park Street | - | Conservation Area Extension | - | Fife Council |
| STA 010 | Hepburn Gardens | - | Conservation Area Extension | - | Fife Council |
| STA 011 | West Sands | 0.3 | New visitor and education centre | - |  |
| STA 012 | Botanic Gardens | 0.5 | Sensitive, small-scale development | - | University of St Andrews/Friends of the Botanic Gardens |
| STA 014 | East Sands | 13 | Development Opportunity | - | Fife Council, University of St Andrews, The Crown Estate, St Andrews Harbour Trust, Private Sector |

St Andrews West Strategic Development Area (STA 001)

      - The development was previously identified as the St Andrews West Strategic Land allocation in the St Andrews & East Fife Local Plan 2012. Development proposals will be tested against the 6 qualities of successful places established in Scottish Government’s Designing Places policy. The requirements for the Stratetic Development Area include:

- 1,090 houses, to be developed on a phased basis in distinct neighbourhoods or “hubs”.

- Masterplanning and arrangements for consultation with the community on the masterplan to be prepared by developers for Fife Council’s approval.

- 1 ha site to be safeguarded for onsite energy generation using CHP/renewables technology.

- Class 4 employment land may be integrated with other uses, including housing, hotel accommodation, care home.

- Local retail opportunities in each of the three “hubs”:

- - University – 400 sq m;

- - Strathkinness – 200 sq m;

- - Craigtoun Road – 2000 sq m.

- Community facilities including place(s) of worship.

- A new community primary school with associated recreation and play facilities;

- 5 ha business park (Class 4).

- 10 ha research and development or Science Park related enterprise.

- 8ha employment land – Classes 4 (business), 5 (general industrial) & 6 (storage & distribution). This will include 6ha at the North Haugh area and 2ha at Craigtoun.

- Road link between A91 and Craigtoun Road to minimise impact of development on the town centre and improve travel around the town.

- Housing north of Strathkinness Low Road will support the planned expansion of the University over the next 20 years. University use and 6.3ha in other ownerships.

      - Green Network Priorities include:

- The development strategy needs to capitalise on the site’s existing landscape assets, high quality setting and scenic value and address the landscape issues.

- Establish new high quality greenspace as an integral part of the wider green network within the site. Combine greenspace with active travel, habitat, sustainable urban drainage and landscape provision.

- Provide high quality landscape and pedestrian and cycle links to connect to the Swilken Green Network (STAGN02); to the Ladebraes Green Network (STAGN01) and to the University Green Network (STAGN04) to establish good connections and integration with the town centre and the coast.

- Develop a new high quality landscape edge with the Swilken Burn corridor (Swilken Green Network (STAGN02)), and the Claremont Burn corridor, which incorporates active travel routes (as part of a St.Andrews south-west round route), and new habitat provision.

- Develop a new high quality landscape edge along the south west boundary, which incorporates active travel routes (as part of a St.Andrews south-west round route) with connections to the wider countryside and new habitat provision and establishes a high quality gateway to St Andrews from the south west.

      - Figure 34 below shows the geographic context of the St Andrew West Strategic Area Framework.

Figure 34. STA 001 St Andrews West

Appendix B. Stakeholder engagement plan

      - This document presents a Stakeholder Engagement Plan, which is designed to support stakeholder engagement through the delivery of Mobility Hubs in East Fife. This plan should be followed throughout the implementation of the hubs at different stages, and it is designed to include different audiences.

      - The key objectives of the stakeholder engagement include:

- Ensure that the vision and objectives for each Mobility Hub align with national, regional and local visions and objectives;

- Build consensus and support from local stakeholders for the concept and benefits of Mobility Hubs in each of the four specific locations;

- Collect feedback from transport operators (both public and private), other service providers such as EV charging providers, technology providers and the local community;

- Assess operational and maintenance requirements and procurement routes; and

- Engage local media and all stakeholders, for example inviting them to an official opening ceremony.

      - For a Mobility Hub to be planned, constructed, operated and monitored successfully, a wide range of stakeholders must be approached and engaged. Key stakeholders have a significant influence on the project and must be managed closely, which can be done by following a stakeholder engagement plan.

      - The stakeholders may include government authorities, public transport operators, community groups, and many other stakeholder types. For this project, a Stakeholder Register was developed with relevant contacts for the planning phase (attached as a separate spreadsheet). The Stakeholder Engagement plan explores the relevance of each stakeholder type as well as the role or activity performed at different stages of the project.

Stakeholder engagement plan

      - The success of Mobility Hubs requires significant involvement of key stakeholders at all phases, from planning through to implementation and evaluation. A Stakeholder Register has been prepared for the planning phase with the relevant contacts (the Register is attached as a sperate spreadsheet).

      - There are two main variables that define stakeholders and how they influence the project:

- Power: the ability of the stakeholder to stop or change direction of the project; and

- Interest: directing the amount of the involvement each stakeholder has in the project.

      - Levels of Power and Interest are used in a common stakeholder analysis technique – a Power-Interest matrix, as shown in Figure 35 below.

      - In the matrix, there are four quadrants each associated with different management characteristics: those with low power and low interest must be monitored; those with high power and low interest must be kept satisfied; those with low power and high interest must be kept informed; and those with high power and high interest must be managed closely as they have a major influence on the project.

Figure 35. Power-Interest Matrix

      - Table 38 below explores the key stakeholders and their roles in the implementation of Mobility Hubs in the East Fife region. The Power-Interest Matrix is used to populate the Approach/Classification field.

      - The Stakeholder Engagement Plan shown in Table 36 presents each stakeholder group and provides examples of the stakeholders that fall under the group. It then explores their relevance and why they should be involved and engaged.

      - Finally, there are details on the role or activities performed at different phases of Mobility Hubs development such as Planning, Construction, Operation and Monitoring. The Stakeholder Engagement Plan presents various stakeholders and type of engagement required at each phase of Mobility Hubs development.

      - It should be noted that the precise role of each stakeholder in operation phase of the Hubs may vary between each hub and will be defined on the completion of the planning phase.

Planning Phase

      - During the planning phase, the development of a detailed implementation plan is required. It will include a wide range of elements, and discussions and partnerships needed to implement the area specific plans over time.

      - The activities to be undertaken include land use and site selection, a technical assessment such as multi-modal transport analysis, and an assessment of key arrangements and contracts required for operation and maintenance of a hub.

      - A major part of stakeholder engagement takes place during this phase, as feedback is needed from public and private transport operators and buy-in is needed from local stakeholders. Stakeholders will be contacted via email; phone calls will be scheduled, and workshops organised as required.

Construction

      - Construction phase will include procurement activities, detailed design and construction of the hubs. Procurement and construction can be arranged by the local authority or any other type of stakeholder depending on operational and contractual agreements for each hub. Engagement with the authority will continue throughout this phase, where progress updates could be made by phone calls. Progress of the contractor/s would be monitored ensuring that the contractor/s stick to the budget and timeline for construction of the hubs.

Operation

      - In order for a Mobility Hub to offer a coherent and seamless experience for users, there should be a stakeholder overseeing the services provided. Comprehensive arrangements should be made for governance as well as agreement on which organisation monitors and manages contractual relationships with partners.

      - The Operation phase includes the day-to-day operation of a Mobility Hub, as well as maintenance, which includes checking that the different components are running correctly and having a regular cleaning schedule. The operator of the hub may be required to collect data on usage of the hub’s components. This will be used in the Monitoring phase of the project.

Monitoring

      - The impact of Mobility Hubs on travel behaviour, usage and wider transport objectives such as carbon emissions and congestion should be monitored to build an evidence base for planning the future expansion/continuation of service provision. Data collected could include number of car club vehicles or bikes rented per day, distance travelled by cars or bikes, number of EV charging instances, etc.

      - Government agencies or transport authorities may commit staff resources to analysing the data, as this would be useful for determining the demand for services, whether there has been any travel behaviour change, or impact on emissions. Defending on a selected operation model, agreements with the Hub operator and mobility providers could be made to ensure the data is collected and shared in a required format.

Table 38. Stakeholder engagement plan

| Stakeholder group | Relevance for engaging | Stakeholders | Areas of influence | Approach / Classification | Role/Activity |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Planning | Construction | Operation | Monitoring |
| Local and regional authorities | Local authorities should be consulted for identifying key locations for Mobility Hubs, based on their role in improving access to employment, education, healthcare and other services. They should also be consulted in relation to any planning requirements associated with implementation of a new Mobility Hub. A Mobility Hub should also be linked to a local legibility/wayfinding strategy. | South East Scotland Transport Partnership (SEStran), Fife Council | Planning and development Acquisition of land Procurement of infrastructure Procurement of services Marketing and promotion Monitoring Ongoing management Staffing Capital funding Revenue funding | These stakeholders would have a medium to high Power and Interest, making them a major influence on the project who need to be Managed Closely. | Inform all departments and utilise council networks to raise awareness. Actively participate in selecting locations and required components of the hubs. Approve the final feasibility study Secure funding for the hubs Allocate land for Mobility Hubs (if applicable) | Manage procurement and tendering process and assign contractor(s) for construction (depending on governance model selected). | Depending on the governance arrangements and operational model selected, support Mobility hubs operations Commit staff resources to continue support the operators in joint promotions (including in any Council publications) and making links to other partners inside and outside the Council. | Undertaking monitoring and evaluation activities allocating required resources. Engage with users via user satisfaction surveys |
| Government | Transport Scotland should be consulted in terms of ensuring Mobility Hubs development and business case occurs within the Strategic Transport Appraisal process Funding can be allocated from the government to sponsor hubs implementation and operation | Transport Scotland, MSPs, Scottish Enterprise, SEPA | Planning and development Ongoing management Marketing and promotion Monitoring Capital funding Revenue funding | Other public bodies have high power but lower level of interest, and need to be Kept Satisfied | Inform all stakeholder departments and utilise council networks to raise awareness. Review proposal and plans for Mobility Hubs. Allocate funding as required | Receive updates on the key procurement and construction timescales and plans | Support promotional activity. Support with funding if required | Assess results of monitoring and evaluation activities. |
| Other government agencies | Other government agencies should be informed and aware of the Mobility Hubs implementation in the area. | Police Scotland, Scottish Fire and Rescue Service, Visit Scotland, NatureScot VisitScotland Cycling Scotland | Planning and development Construction Ongoing management Marketing and promotion | These stakeholders could have low power and low interest, and need to be Monitored | To be aware of the plans to develop Mobility Hubs | Receive updates on the key procurement and construction timescales and plans | Support promotional activity | N/A |
| Public transport operators | In addition to providing services, operators may also share real-time data on fleet, timings, ridership and utilisation of Mobility Hubs. This will help to monitor performance and identify challenges of Mobility Hubs once implemented. Operators could also be approached for funding, or managing some locations, as the implementation of the hubs could positively impact the operators’ ridership and revenue. | ScotRail, Stagecoach, Other local bus operators | Planning and development Provision of services Service level agreements Information provision Marketing & promotion Provision of monitoring data Funding Management | Operators need to be Kept Satisfied or Managed Closely. | Create a common positive narrative and listen to feedback. Participate in the development and design of the hub. Contribute to funding | Keep informed on the progress of construction, providing input as needed. | Depending on the governance arrangements and operational model selected, support Mobility hubs operations. Support promotional activity | Engage with users via user satisfaction surveys. Collect data on usage and travel behaviour. |
| Shared mobility and other private transport operators | Mobility services, such as bike share, car clubs, on-demand bus services, taxi/private hire vehicles, and shared e-scooters are pivotal to deliver improved connectivity which does not rely on private cars. Additionally, first mile / last mile freight services can also be offered through Mobility Hubs, such as e-cargo bikes. The suppliers of shared mobility services will need to be consulted to consider the commercial aspects of potential Mobility Hubs and the extent to which these services can be provided commercially, or whether funding is required. | Go e-bike scheme, St Andrews Bike Pool, Car club operators (Co-wheels, Enterprise, Ubeeqo), Bike share providers | Planning and development Provision of services Service level agreements Information provision Marketing & promotion Provision of monitoring data Funding Management | Shared mobility and private operators would need to be Kept Satisfied or Managed Closely depending on how much input is required | Create a common positive narrative and listen to feedback. Participate in the development and design of the hub. Contribute to capital funding | Keep informed on the progress of construction, providing input as needed. | Depending on the governance arrangements and operational model selected, support Mobility hubs operations Support promotional activity Contribute to revenue funding | Engage with users via user satisfaction surveys. Collect data on usage and travel behaviour. |
| Local community groups including residents and businesses | The local community and businesses are the primary users of Mobility Hubs. They should be consulted at an early stage of development to understand their current mobility needs and challenges. In order to get political buy-in, involvement of local councillors is also recommended. This can have the added benefit of increasing the profile of Mobility Hubs and securing public support and take-up. | CLEAR Buckhaven & Methil, BRAG, Community Councils, Families First St Andrews, Fife Voluntary Action, Leuchars Community Council, Levenmouth Rail Campaign (LMRC), The Leven Partnership, Local Community Planning Partnership, Fife Councillors, Local business groups | Planning and development Provision of land/infrastructure Marketing & promotion Capital funding contribution Revenue funding contribution | These groups have high power and lower or high interest and must be Kept Satisfied or Managed Closely | Contribute to specifications and design of the hubs. | Keep community groups informed on progress of the project, for example if there are delays | Depending on the governance arrangements and operational model selected, support Mobility hubs operations Potential to manage the hub or services depending on their location. Support promotional activities. Continue to share information in premises and online in particular with special events. | Work with the operator and Council to keep informed on take up of Mobility Hub features, making use of collected data to keep members, residents and businesses informed. |
| Not-for-profit organisations including disability and other community groups | Mobility Hubs aim to improve accessibility for all transport users. Hence, feedback on needs and challenges from those who may be most impacted by poor accessibility would help in developing inclusive services that cater to the requirements of the wider community. Key groups to consider would include those with mobility difficulties, the elderly, younger people, those from areas of high deprivation. Consultation with organisations such as CoMoUK and Sustrans would be essential. | CoMoUK, Fife Centre for Equalities, Forth Rivers Trust, Fife Coast & Countryside Trust, Go e-bike scheme, Green Action Trust, Keep Scotland Beautiful, Paths for All, Sustrans, Zero Waste Scotland, Levenmouth Local Tourist Association, Transition St Andrews, Stay St Andrews Tourist Board, Living Streets | Planning and development Provision of land/infrastructure Marketing & promotion Capital funding contribution Revenue funding contribution | These groups have a high interest and low to high power and must be Kept Informed or Kept Satisfied | Contribute to specifications and design of the hubs. Contribution to capital and revenue funding | Keep informed on the progress of construction | Depending on the governance arrangements and operational model selected, support Mobility hubs operations Encourage members to attend launch events and try the scheme Support promotional activities | Monitor and evaluation activities |
| Major employment sites, property developers and other key trip generators | Major employment sites (such as large business parks) or other key generators such as a large hospital or educational sites, are key stakeholders. A local authority needs to make them aware of a potential for a Mobility Hub to be developed in the areas and gather their feedback and thoughts. | Diageo James Donaldson Timber, Cameron hospital, NHS Fife University of St Andrews, James Donaldson Timber, British Army, housing developments | Planning and development Provision of land/infrastructure Marketing & promotion Capital funding contribution Revenue funding contribution | These stakeholders would have high power and lower or high interest depending on an individual hub They should be Managed Closely or Kept Satisfied | Contribute to design of mobility hubs and its components. Influence section of the sites for the hubs Contribute to funding of the hubs Allocate land for Mobility Hubs (if applicable) | Manage procurement and tendering process and assign contractor(s) for construction (depending on governance model selected)/ or Be informed about construction plans | Depending on the governance arrangements and operational model selected, support Mobility hubs operations Share scheme information through internal networks, host try out sessions. Promote particularly to new residents/employees and at times of special events. | Receive data on Mobility Hub usage and travel trends. |
| Technology providers | The back-end technology that supports and manages journey planning, payment systems, real time information, user interfaces such as mobile applications and contact centre, also plays a significant role in user demand and user acceptance of Mobility Hubs. In addition, mobile service providers should be appropriately involved to power the systems or provide wi-fi connections at the hubs. | Wi-fi providers, MaaS operators, journey planning apps, ticketing providers JustPark, RingGo | Planning Back-end Technology User Interfaces Data Sharing Payment Solutions | These stakeholders would have low Power and high Interest, needing to be Kept Informed. | To be consulted during the planning phase | Involved as required to ensure relevant communications connection are in place | Operate their services at the hubs Support operator’s promotional activity | Collect and share data on usage and travel behaviour. |
| Assets, infrastructure and utility companies | Physical assets and infrastructure, including charging stations for EVs, and smart kiosks/ information pillars for wayfinding and ticketing, can be included at Mobility Hubs. Additional features such as vending machines, coffee carts, co-working spaces and others can be further developed at Mobility Hubs. | ChargePlace Scotland, Network Rail Scottish Water | Planning and development Provision of infrastructure | Kept informed/ Managed Closely depending on the level of involvement. | The suppliers could be consulted in the planning phase to explore key features that can be built at the hubs. In case of Network Rail - collaborate on the final design of the station in Levenmouth area, agree on funding and key features of the hubs | Involved as required depending on procurement outcomes In case of Network Rail – build the station and provde required assets for the hubs as agreed in the planning phase | Operate their services at the hubs Support operator’s promotional activity | Collect and share data on usage (if applicable depending on each stakehodler) |
| Local media | Local media could contribute to raising the profile of the launch or circulating information about special offers and opportunities. For example, a journalist could test ride different modes of transport or components of the Mobility Hub and thus generate interest from the media and community. | Local media and newspapers | Marketing and promotion | Media would be low power and potentially high interest depending on marketing and relationships with the public authorities, for example, needing to be Kept Informed. Could be Managed Closely depending on how vocal/influential the local media is | N/A | Echo narrative of the scheme development with positive news stories. Raise profile of the launch, PR stunts, special offers and try out opportunities. | Promote new hubs, special offers, milestones and good news stories /case studies. | N/A |
| Other established Mobility Hubs | There is a growing range of Mobility Hubs implemented internationally and in the UK. Each site presents a potentially valuable stakeholder in terms of sharing knowledge and expertise on best practice for implementation and operation of Mobility Hubs in East Fife. Ongoing engagement will be valuable to share lessons learnt and identify how challenges have been overcome and how opportunities have been harnessed. | Hubs in Redbridge, UK BP Mobility hub in London, WECA, UK (planned Mobility Hubs) Solent, UK (planned Mobility Hubs) Derby and Nottingham, UK (planned Mobility Hubs) and other locations Hubs in Austria, Germany, Norway, Netherlands | Planning Experience Operational Experience Monitoring and evaluation | These stakeholders could be low power and low interest, needing to be Monitored | Knowledge share | Knowledge share | Knowledge share | Knowledge share |

Control Information

| Prepared by |  | Prepared for |
| --- | --- | --- |
| Steer 28-32 Upper Ground London SE1 9PD +44 20 7910 5000 www.steergroup.com |  | SEStran Area 3D (Bridge) Victoria Quay Edinburgh EH6 6QQ |

| Steer project/proposal number |  | Client contract/project number |
| --- | --- | --- |
| 24097601 |  |  |

| Author/originator |  | Reviewer/approver |
| --- | --- | --- |
| Olga Anapryenka, Susmita Das, Daniel Almazan Becerra, Sekai Zengeza, Antonia Roberts |  | Matthew Clark, Tom Higbee |

| Other contributors |  | Distribution |
| --- | --- | --- |
| Aashni Patel, Shipra Bhatia, Daniel Almazan Becerra, Edmund Cassidy, Hannah Thompson, Alia Verloes, Iain Weir |  | Client: |  | Steer: |  |

| Version control/issue number |  | Date |
| --- | --- | --- |
| First revision_v1.1 |  | 26/11/21 |

SEStran-Mobility-Hubs-Strategic-Study-Final-Report.pdf

How - CoMoUK

SEStran-Mobility-Hubs-Strategic-Study-Final-Report.pdf

http://www.explore-st-andrews.com/trips-and-tours/st-andrews-buses/

Mechanical, electrical and plumbing

The data is provided by St Andrews University

CoMoUK_Mobility-Hubs_Breman-Case-Study.pdf

Re-imagining the Urban Form – Austin USA: https://rmi.org/wp-content/uploads/2018/12/rmi-mobility-hub-report-2018.pdf

Case study Bike sharing system Hello Bike on the Zuidas Amsterdam - Rijkswaterstaat Environment (rwsenvironment.eu). The evidence provided by CoMoUK

The City of Vienna’s Mobility Hubs Guidelines, Page 25: https://www.wien.gv.at/stadtentwicklung/studien/pdf/b008521.pdf

The evidence is provided by CoMoUK

Bremen case study: https://como.org.uk/wp-content/uploads/2021/01/CoMoUK_Mobility-Hubs_Breman-Case-Study.pdf

Wirksamkeit Mobilitätskonzepte (Effectiveness of Mobility concepts): http://mf.team-red.de/index.php?id=143

CoMoUK-Scotland-Bike-Share-Survey-2020.pdf

SMMT

Public attitudes towards electric vehicles: February 2016 (revised) (publishing.service.gov.uk)

CoMoUK-Bike-Share-Survey-2020-FINAL_compressed-1.pdf

Bremen case study: https://como.org.uk/wp-content/uploads/2021/01/CoMoUK_Mobility-Hubs_Breman-Case-Study.pdf=

CoMoUK-Bike-Share-Survey-2020.pdf

https://tfl.gov.uk/info-for/media/press-releases/2021/january/santander-cycles-welcomes-record-new-users-during-its-tenth-anniversary-year

Steer visualises London Cycle Hire trips during lockdown | Steer (steergroup.com)

https://www.edinburghnews.scotsman.com/news/transport/coronavirus-in-scotland-cycling-boom-as-number-of-cyclists-increased-in-lockdown-3190044

https://www.glasgowlive.co.uk/news/glasgow-news/glasgow-spaces-people-changes-made-21559884

Source: DataShine Scotland that utilises the DataShine framework to map selected Quick Statistics and Key Statistics for Scotland’s 2011 Census.

Calculated based on the current timetable of bus services at St Andrews Station, with an assumption on users per bus (5-10) and an uncertainty adjustment factor of 0.75.

Source: CoMoUK bike share map https://como.org.uk/shared-mobility/shared-bikes/where/

E-bikes for the Bicing scheme makes 9 trips per day, compared to 6 trips on standard bikes. Similarly, while 35% of Velib fleet is electric, more than 50% of total trips are made on e-bikes.

CoMoUK-Bike-Share-Survey-2020-FINAL_compressed-1.pdf

CoMoUK-Scotland-Car-Club-Summary-Report-2020.pdf

The economic appraisal element within STAG typically users guidance and parameters based on UK guidance, which is updated on a more regular basis.

https://communitysharesscotland.org.uk

https://www.thebank.scot

Places for Everyone - Sustrans.org.uk

Smarter Choices, Smarter Places Local Authority Fund | Paths for All

eBike Grant Fund available in Scotland - Energy Saving Trust

https://www.cycling.scot/what-we-do/cycling-friendly/community

Cycle fund | ScotRail

Low Carbon Travel and Transport Challenge Fund - Energy Saving Trust

https://www.standrewscommunitytrust.co.uk/

https://www.tnlcommunityfund.org.uk/funding/programmes/national-lottery-awards-for-all-scotland#section-1

Further funding to provide alternatives to car ownership (transport.gov.scot)

Regeneration: Capital investment for regeneration - gov.scot (www.gov.scot)

Rural Development Fund - Funding | VisitScotland.org

https://como.org.uk/wp-content/uploads/2020/11/Mobility-Hub-Accreditation-111120-1.pdf

Source: DataShine Scotland that utilises the DataShine framework to map selected Quick Statistics and Key Statistics for Scotland’s 2011 Census.

Levenmouth Connectivity project final report - active travel report

https://simd.scot/#/simd2020/BTTTFTT/13.235400010369375/-2.8551/56.3506/

Transition University St Andrew, 2021, A Public Bike Share Scheme, Worth it? (site visited on 9/24/2021)

Sustrans

https://tiscon-maps-stagecoachbus.s3.amazonaws.com/RouteMaps/East%20Scotland/ESCOT_MAP_StAndrews.pdf

https://www.transitionsta.org/blogs/2021/07/64888/

http://arcgisweb.fife.gov.uk/LocalViewEXT/Sites/LDP1adopted/?extent=347508,714727,352521,717859&sr=27700

Where - CoMoUK